## Slide 1
FORESTRY
RM 8 bil in exports by 2030
MUDeNR Outcome:
Increase Timber & Non Wood Forest Products Exports Earnings
Community-Based Ecotourism and conservation Totally Protected Area
Certify Long Term Forest License Area and Forest Plantation
200,000 ha degraded area (100%) planted/restored by 2030
Obtain world recognition for sustainable management practices and conservation effort
Q2 2025
Program
Q2 2025 Target
Rating
Q2 2025 Status
3. 5 . System Tagang
To implement 2 locations Tagang in Sarawak surounding TPAM.
"1. BRO: Project proposal for 1 potential sites submitted and approved.
2. SRO: Organized Workshop to Develop System Tagang Project Proposal at Sg Betun with DOA.
Bamboo Industry Development
To plant 750 ha of bamboo target cumulative for half yearly 2025
To produce 200,000 seedlings cumulative for half yearly 2025
To proposed nursery plan, site identification, manpower and implementation planning (half yearly 2025)
in progress :
Jan - June 2025 = 5.75 hectares planted
in progress :
Sabal - 2,879 seedlings produced
Tg Manis - 134,764 seedlings produced
Total Jan - June 2025 = 137,643 seedlings produced
in progress :
- Site visit to Kompleks Industri Perabot PUSAKA Kuala Baram (KIPPKB)
- Discussion on KIPPKB facilities via zoom meeting
Timber Export Value (RM)
'25 Total
RM 0.00
'24 Total
RM 2,128,434,989
Chart: 
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2024 Export Value | 276004972.69 | 191530929.47 | 214907671.7 | 232014272.14 | 324627750.87 | 212303812.34 | 274788036.68 | 210420404.31 | 191837139 | 0 | 0 | 0
2025 Export Value | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPA Protection & Biodiversity Conservation Programs (incl. community-based initiatives
32
On-going programs and initiatives by SFC (as of Sept 2024)
Obtain world recognition for sustainable management practices and conservation effort
50%
SDGP UNESCO Global Geopark
(as of Sept 2024)
100%
Niah NP UNESCO World Heritage Site
(as of Sept 2024)
Certification of FMU & FPMU
56.7%
1,703,164 ha Certified (May 2025)
Legend:
Monthly target achieved, Project on track
Miss in target but still on track for 2025
Severe delays
Not started
2024
2025
DRAFT 19 June 2025
Total Degraded Area (Ha)
Chart: 
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2022 | 787.01 | 912.41 | 513.04 | 428.18 | 485.08 | 1277.9 | 745.15 | 762.69 | 579.09 | 676.27 | 2012.35 | 1114.64
2023 | 1856.37 | 3449.94 | 2284.69 | 1807.69 | 3255.8 | 3120.66 | 2562.38 | 2474.93 | 3251.93 | 3086.64 | 3081.63 | 3240.14
2024 | 3572.12 | 6911.42 | 3565.31 | 2243.09 | 3190.19 | 3618.48 | 1378.09 | 1536.83 | 1141.79 | 1311.2 | 942.5 | 969