## Slide 1
FORESTRY
RM 8 bil in exports by 2030
MUDeNR Outcome:
Increase Timber & Non Wood Forest Products Exports Earnings
Community-Based Ecotourism and conservation Totally Protected Area
Certify Long Term Forest License Area and Forest Plantation
200,000 ha degraded area (100%) planted/restored by 2030
Obtain world recognition for sustainable management practices and conservation effort
Q2 2025
Program
Q2 2025 Target
Rating
Q2 2025 Status
Proposed Implementation of Forest Landscape Restoration Throughout Sarawak
Cumulative of 50million trees planted and recorded in Penghijauan Malaysia
15 CEPA/planting programs in collaboration with various stakeholders conducted
49,000,000 million trees planted
15 CEPA/planting programs in collaboration with various stakeholders conducted
Conservation and Protection of Wetlands and Watershed Within Heart of Borneo Sarawak
Engagement session on project implementation of P.17 Conservation and Protection of Wetlands and Watershed Within Heart of Borneo Sarawak (HoB)
Project planning meeting of P.17 on Conservation and Protection of Balleh Watershed, Kapit
Field survey on Wetlands area for P.17 Conservation and Protection of Wetlands and Watershed Within Heart of Borneo Sarawak (HoB)
Discussion on CEPA Program for community in Paloh/Loba Pulau
One Engagement session on project implementation of P.17 Conservation and Protection of Wetlands and Watershed Within Heart of Borneo Sarawak (HoB) have been done
Meeting on project planning and Human Capital Skills Program on Conservation and Protection of Balleh Watershed, Kapit
Field survey activities for natural tourist attractions and tourism potential in the proposed Ramsar site area
One CEPA Program for community in Paloh have been approved and will be held on July
Quantifying Forest Carbon Stock in Sarawak
1. Organize conference to monitor carbon permit and license holder status
2. Prepare sebutharga and tender doc for car rental and other purchases.
3. Conduct field survey to look for virgin peat swamp forest.
4. Carry out sampling at Anap Muput FMU.
5. Organize training on soil sustainability and management.
Conduct one carbon training at Netherland in June.
One sampling trip to Peat Swamp Forest at Sebuyau.
1. Conference was conducted at Miri on 25 & 26 Feb 2025.
2. Meeting to discuss the spec after receiving document from bidders was conducted on 10 Apr. However, major mistake on the RDD transport rental document and need to retender.
3. Recce was carrid out in Mar and potential site is at Kanowit.
postpone due to no transportation
Application to Datu was rejected
Postpone to Sept due to IDF event fall on 29/6
It was carried out on 8-21 May 2025
Bamboo Industry Developement 2026
plan to plant 1000 hectar
in programess
Furniture Park
Submission of Budget for Development (Demak Laut) by 1st Half 2025
Submission of Budget for Development (Tanjung Manis) by 1st Half 2025
RMK13 budget interview by 2nd Half 2025
2 Potential investor enggagement session
RM233,709.000.00 for full development of Infra (Clearing, Soil Treatment, Land Dev, Infra Build Up, Fencing, ETC) submitted to MUDeNR on 29 May 2025
RM14,000.000.00 for development of Infra (P&G,Fencing,11kv Sub,Soil Investigation,ETC) submitted to MUDeNR on 29 May 2025
Preparation for the budget Interview (expected in July)
at least 2 potential investor engaged for both furniture park
Strengthening Forest Enforcement Through Advancing the Technology and Equipments
1. Processing of Tender document (waiver) on rental of land and river transport for forest enforcement operation - 5 tender documents at Sarikei, Sibu, Kapit, Bintulu and Miri Region
An integrated forest enforcement operation on combating illegal logging and encroachment within Permanent Forest Estates - 5 operation
Training for forest enforcement officers - 5 training program
Awareness program on forest enforcement - 5 program
Completed
In progress - Three (3) integrated forest enforcement operation conducted on combating illegal logging and encroachment within Permanent Forest Estates
In progress - Three (3) trainings conducted for forest enforcement officers
In progress - Two (2) awareness program on forest enforcement conducted
Niah Unesco
t1 aaa
t2 bbb
50% certified
100% certified
Timber Export Value (RM)
'25 Total
RM 0.00
'24 Total
RM 2,128,434,989
Chart: 
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2024 Export Value | 276004972.69 | 191530929.47 | 214907671.7 | 232014272.14 | 324627750.87 | 212303812.34 | 274788036.68 | 210420404.31 | 191837139 | 0 | 0 | 0
2025 Export Value | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPA Protection & Biodiversity Conservation Programs (incl. community-based initiatives
32
On-going programs and initiatives by SFC (as of Sept 2024)
Obtain world recognition for sustainable management practices and conservation effort
50%
SDGP UNESCO Global Geopark
(as of Sept 2024)
100%
Niah NP UNESCO World Heritage Site
(as of Sept 2024)
Certification of FMU & FPMU
56.7%
1,703,164 ha Certified (May 2025)
Legend:
Monthly target achieved, Project on track
Miss in target but still on track for 2025
Severe delays
Not started
2024
2025
DRAFT 23 June 2025
Total Degraded Area (Ha)
Chart: 
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2022 | 787.01 | 912.41 | 513.04 | 428.18 | 485.08 | 1277.9 | 745.15 | 762.69 | 579.09 | 676.27 | 2012.35 | 1114.64
2023 | 1856.37 | 3449.94 | 2284.69 | 1807.69 | 3255.8 | 3120.66 | 2562.38 | 2474.93 | 3251.93 | 3086.64 | 3081.63 | 3240.14
2024 | 3572.12 | 6911.42 | 3565.31 | 2243.09 | 3190.19 | 3618.48 | 1378.09 | 1536.83 | 1141.79 | 1311.2 | 942.5 | 969