## Slide 1
FORESTRY
RM 8 bil in exports by 2030
MUDeNR Outcome:
Increase Timber & Non Wood Forest Products Exports Earnings
Community-Based Ecotourism and conservation Totally Protected Area
Certify Long Term Forest License Area and Forest Plantation
200,000 ha degraded area (100%) planted/restored by 2030
Obtain world recognition for sustainable management practices and conservation effort
Half Year 1 2025
Program
Half Year 1 2025 Target
Rating
Half Year 1 2025 Status
Proposed Implementation of Forest Landscape Restoration Throughout Sarawak
Cumulative of 50million trees planted and recorded in Penghijauan Malaysia
15 CEPA/planting programs in collaboration with various stakeholders conducted
49,000,000 million trees planted
15 CEPA/planting programs in collaboration with various stakeholders conducted
Conservation and Protection of Wetlands and Watershed Within Heart of Borneo Sarawak
No target set
No status update available
Quantifying Forest Carbon Stock in Sarawak
No target set
No status update available
Bamboo Industry Development
To plant 750 ha of bamboo target cumulative for half yearly 2025
To produce 200,000 seedlings cumulative for half yearly 2025
To proposed nursery plan, site identification, manpower and implementation planning (half yearly 2025)
in progress :
Jan - June 2025 = 5.75 hectares planted
in progress :
Sabal - 2,879 seedlings produced
Tg Manis - 134,764 seedlings produced
Total Jan - June 2025 = 137,643 seedlings produced
in progress :
- Site visit to Kompleks Industri Perabot PUSAKA Kuala Baram (KIPPKB)
- Discussion on KIPPKB facilities via zoom meeting
Furniture Park
Submission of Budget for Development (Demak Laut) by 1st Half 2025
Submission of Budget for Development (Tanjung Manis) by 1st Half 2025
RMK13 budget interview by 2nd Half 2025
2 Potential investor enggagement session
RM233,709.000.00 for full development of Infra (Clearing, Soil Treatment, Land Dev, Infra Build Up, Fencing, ETC) submitted to MUDeNR on 29 May 2025
RM14,000.000.00 for development of Infra (P&G,Fencing,11kv Sub,Soil Investigation,ETC) submitted to MUDeNR on 29 May 2025
Preparation for the budget Interview (expected in July)
at least 2 potential investor engaged for both furniture park
3.2 Management and Strengthening Protection for Selected Totally Protected Areas
No target set
No status update available
Research and Development for KURSI PUSAKA in UNIMAS
To develop and produce the furniture prototypes.
To conduct Research on Design As Catalyst To Develop The Fine Fabrics From Bamboo Textiles In Sarawak. (24 Months Project)
In progress - In the process of identifying vendor and preparing details of prototype design.
In progress - MoA signed. Project expected to start in 2nd quarter.
Strengthening Forest Enforcement Through Advancing the Technology and Equipments
No target set
No status update available
Timber Export Value (RM)
'25 Total
RM 0.00
'24 Total
RM 2,128,434,989
Chart: 
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2024 Export Value | 276004972.69 | 191530929.47 | 214907671.7 | 232014272.14 | 324627750.87 | 212303812.34 | 274788036.68 | 210420404.31 | 191837139 | 0 | 0 | 0
2025 Export Value | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPA Protection & Biodiversity Conservation Programs (incl. community-based initiatives
32
On-going programs and initiatives by SFC (as of Sept 2024)
Obtain world recognition for sustainable management practices and conservation effort
50%
SDGP UNESCO Global Geopark
(as of Sept 2024)
100%
Niah NP UNESCO World Heritage Site
(as of Sept 2024)
Certification of FMU & FPMU
56.7%
1,703,164 ha Certified (May 2025)
Legend:
Monthly target achieved, Project on track
Miss in target but still on track for 2025
Severe delays
Not started
2024
2025
DRAFT 10 July 2025
Total Degraded Area (Ha)
Chart: 
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2023 | 1856.37 | 3449.94 | 2284.69 | 1807.69 | 3255.8 | 3120.66 | 2562.38 | 2474.93 | 3251.93 | 3086.64 | 3081.63 | 3240.14
2024 | 3572.12 | 6911.42 | 3565.31 | 2243.09 | 3190.19 | 3618.48 | 1378.09 | 1536.83 | 1141.79 | 1311.2 | 942.5 | 969
2025 | 5.6 | 86.5 | 62.2 | 127.3 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0