## Slide 1
FORESTRY
RM 8 bil in exports by 2030
MUDeNR Outcome:
Increase Timber & Non Wood Forest Products Exports Earnings
Community-Based Ecotourism and conservation Totally Protected Area
Certify Long Term Forest License Area and Forest Plantation
200,000 ha degraded area (100%) planted/restored by 2030
Obtain world recognition for sustainable management practices and conservation effort
Q2 2025
Program
Q2 2025 Target
Rating
Q2 2025 Status
Program A
target 1; target 2
N/A
Timber Export Value (RM)
'25 Total
RM 0.00
'24 Total
RM 2,128,434,989
Chart: 
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2024 Export Value | 276004972.69 | 191530929.47 | 214907671.7 | 232014272.14 | 324627750.87 | 212303812.34 | 274788036.68 | 210420404.31 | 191837139 | 0 | 0 | 0
2025 Export Value | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPA Protection & Biodiversity Conservation Programs (incl. community-based initiatives
32
On-going programs and initiatives by SFC (as of Sept 2024)
Obtain world recognition for sustainable management practices and conservation effort
50%
SDGP UNESCO Global Geopark
(as of Sept 2024)
100%
Niah NP UNESCO World Heritage Site
(as of Sept 2024)
Certification of FMU & FPMU
78%
FMU
2,327,221 ha Certified (Sept 2024)
69%
FPMU
122,800 ha Certified (Sept 2024)
Legend:
Monthly target achieved, Project on track
Miss in target but still on track for 2025
Severe delays
Not started
2024
2025
DRAFT 18 June 2025
Total Degraded Area (Ha)
Chart: 
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2022 | 787.01 | 912.41 | 513.04 | 428.18 | 485.08 | 1277.9 | 745.15 | 762.69 | 579.09 | 676.27 | 2012.35 | 1114.64
2023 | 1856.37 | 3449.94 | 2284.69 | 1807.69 | 3255.8 | 3120.66 | 2562.38 | 2474.93 | 3251.93 | 3086.64 | 3081.63 | 3240.14
2024 | 3146.6 | 6660.5 | 3203.8 | 1871.5 | 2750.2 | 3396.3 | 0 | 0 | 0 | 0 | 0 | 0