## Slide 1
FORESTRY
RM 8 bil in exports by 2030
MUDeNR Outcome:
Increase Timber & Non Wood Forest Products Exports Earnings
Community-Based Ecotourism and conservation Totally Protected Area
Certify Long Term Forest License Area and Forest Plantation
200,000 ha degraded area (100%) planted/restored by 2030
Obtain world recognition for sustainable management practices and conservation effort
Q5 2025
Program
Q5 2025 Target
Rating
Q5 2025 Status
Furniture Park
No target set
No status update available
Timber Export Value (RM)
'25 Total
RM 0.00
'24 Total
RM 2,128,434,989
Chart: 
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2024 Export Value | 276004972.69 | 191530929.47 | 214907671.7 | 232014272.14 | 324627750.87 | 212303812.34 | 274788036.68 | 210420404.31 | 191837139 | 0 | 0 | 0
2025 Export Value | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPA Protection & Biodiversity Conservation Programs (incl. community-based initiatives
32
On-going programs and initiatives by SFC (as of Sept 2024)
Obtain world recognition for sustainable management practices and conservation effort
50%
SDGP UNESCO Global Geopark
(as of Sept 2024)
100%
Niah NP UNESCO World Heritage Site
(as of Sept 2024)
Certification of FMU & FPMU
78%
FMU
2,327,221 ha Certified (Sept 2024)
69%
FPMU
122,800 ha Certified (Sept 2024)
Legend:
Monthly target achieved, Project on track
Miss in target but still on track for 2025
Severe delays
Not started
2024
2025
DRAFT 18 June 2025
Total Degraded Area (Ha)
Chart: 
| JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
2022 | 787.01 | 912.41 | 513.04 | 428.18 | 485.08 | 1277.9 | 745.15 | 762.69 | 579.09 | 676.27 | 2012.35 | 1114.64
2023 | 1856.37 | 3449.94 | 2284.69 | 1807.69 | 3255.8 | 3120.66 | 2562.38 | 2474.93 | 3251.93 | 3086.64 | 3081.63 | 3240.14
2024 | 3146.6 | 6660.5 | 3203.8 | 1871.5 | 2750.2 | 3396.3 | 0 | 0 | 0 | 0 | 0 | 0