## Aspiration
Aspiration Framework for Foresty Sector
| 3 | Certify 3 mil ha of long term forest licence area and 178,000 ha forest plantation under Malaysian Timber Certification Council/Programme for the Endorsement of Forest Certification and Forest Stewardship Council

## Outcome Linked (OL) (hidden)
FORESTRY SECTOR
| KEY OUTCOME : | 1. Increase timber & non wood forest products export earnings - Annual export value of RM8 billion by 2030 2. 50 community-based ecotourism and conservation Totally Protected Areas 3. Certify 3 mil ha of long term forest licence area and 178,000 ha forest plantation under Malaysian Timber Certification Council/Programmes for the Endorsement of Forest Certification and Forest Stewardship Council
DEFINITION :
| OUTCOME | Prior Year | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | Remark
| 1. Increase timber & non wood forest products export earnings - Annual export value of RM8 billion by 2030 | 2022: RM3.9 bil | RM4 Billion |  | Jan-June: RM1.5 mil |  | RM4 Billion |  |  |  | RM4 Billion | [19 empty] | RM 8 billion
| 2. 50 community-based ecotourism and conservation Totally Protected Areas |  | SFC: 53 [29 completed + 24] |  |  |  | 26 |  |  |  | 33 | [19 empty] | 50
| 3. Certify 3 mil ha of long term forest licence area and 178,000 ha forest plantation under Malaysian Timber Certification Council/Programmes for the Endorsement of Forest Certification and Forest Stewardship Council | FMU- 2022: 202,000 ha FPMU 2022: 35,860 ha | 60% (FMU) 55% (FPMU) |  | FMU- Jan-June: 460,934 ha FPMU- Jan-June: 58,994 ha |  | 80% (FMU) 75% (FPMU) |  |  |  | 100% (FMU) 100% (FPMU) | [19 empty] | 3 mil ha (natural forest); 178,000 ha forest plantation
| 4. 200,000 ha area (100%) planted/restored by 2030 | 2022 = 10,293.82 ha | 10% area planted/restored in year 2023 |  | Current restored area (Jan-June) : 15,191.76 ha |  | 10% ha area planted/restored in year 2024 |  |  |  | 10% ha area planted/restored in year 2025
| 5. Obtain world recognition for sustainable management practices and conservation effort | 1. SDGp was endorsed as national geopark on 20 June 2022 | 1. Preparation of SDGp management plan. - Commencement of Study on SDGp Development and Management Plan 2040. - Producing Interim Report of Study by end of 2023. 2. Preparation of application dossier 3. Engagement with national expert group 4. Increase visibility through signage and information panels 5. Initiate SDGp website 6. Produce promotional materials for SDSGp 7. initiative such as bulletin, coffee table books and corporate video 8. Completion of upgrading of Gallery in Damai Central |  | 1.Instalation of signage "I LOVE Sarawak Delta geopark" at Bung Jagoi & Kpg Sapit. 2. Sarawak Delta geopark Expedition, 2023. |  | 1. Completion of SDGp Development and Management Plan 2040. 2. Letter of intent to be submitted to UNESCO before July 2024. 3. Completion of nomination dossier. 4. Nomination Dossier to be submitted to UNESCO in October - November 2024. |  |  |  | 1. Evaluation by UNESCO by 2025. 2. To be recognised as UNESCO Global Geopark by 2026.
|  | 1. Tentative List for Niah National Park has been submitted to UNESCO on 30 January 2022. | 1. Niah National Park as UNESCO World Heritage Site Assessment/Evaluation of Niah NP by ICOMOS. |  | 1. Nomination dossier for Niah National Park has been submitted to UNESCO on 30 January 2023. 2. Assessment by ICOMOS was carried out on 29/9-4/10/2023 |  | 1. Niah NP successfully inscribed as a WHS. *Streamlining the protection and management of Niah NP with the Operational Guidelines for the Implementation of the World Heritage Convention Note: In the event inscription is unsuccessful, there will be another level of improvement of the property that needs to be done to fulfil the inscription requirement e.g. Management of the conservation/ archaeological sites etc. |  |  |  | 1. Niah NP successfully inscribed as a WHS. *Streamlining the protection and management of Niah NP with the Operational Guidelines for the Implementation of the World Heritage Convention Note: In the event inscription is unsuccessful to follow through all Management plans accordingly to ensure that the property is managed and developed sustainably.
|  |  | Plan |  | Achievement |  | Plan |  | Achievement |  | Plan |  | Achievement | [17 empty] | Plan |  | Achievement
| Programmes Impacting to the Outcome |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | Remark
|  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
| Generate government revenue by developing new revenue streams from forest resources | O1/O2/O3/O4/O5
1 | Formulate Sarawak Climate Change Policy and Low Carbon Society Blueprints | O1/O2/O3/O4/O5 | bar: 2023 Q1
1.1 | Preparation of TOR and Procurement of Consultancy services in accordance with the Manual Perolehan Perkhidmatan Perunding Kerajaan Negeri
1.2 | Appointment of Consultant to undertake the work |  | 2023 Q2: 2023-05-15
1.3 | Undertake the Study with the desire to attain the following outcomes by 2030: |  | 2024 Q4: 2024-11-14
1.3.1 | 5% of SME derived from green economies by 2030
1.3.2 | 5% of the job created are green jobs by 2030.
1.3.3 | Reduction of Carbon (GHG) emission as much as 45% by 2030.
1.3.4 | Increased Infrastructure Resiliency up to 80%.
1.3.5 | Daily API in Kuching, Miri, Sibu and Bintulu to be reduced/maintained to healthy level (API below 50).
1.4 | Seek endorsement from the Minister/MMKN on the proposed Sarawak Climate Change Policy and Low Carbon Cities Blueprints in Cities and Towns in Sarawak
1.5 | Monitor the implementation of action plans and desire outcomes
2 | Establish Permanent Sample Plot Network In Sarawak | O3/O5 | bar: 2023 Q1
2.1 | Establishment and assessment of permanent sample plot network in FMU area | bar: 2023 Q1 to 2025 Q4; 2030 Q4
2.2 | Engage mapping consultant for forest structure mapping using LiDAR technology | bar: 2023 Q3 to 2024 Q1; 2026 Q1 to 2030 Q4
2.3 | Engage expert for development of growth and yield projection model
2.4 | Hire local community for the implementation of plot establishment and collection of field data
2.5 | Conduct forest structure mapping using UAV LiDAR technology | bar: 2024 Q1 to 2025 Q2; 2026 Q1 to 2030 Q4
2.6 | Develop and apply growth and yield projection model for comprehensive and reliable analysis | bar: 2024 Q2 to 2030 Q4
2.7 | Analyse and share research findings with stakeholders | bar: 2023 Q4 to 2024 Q3; 2025 Q1 to 2030 Q4
3 | Establishment of Centre of Excellence for Planted Forest R&D | O3/O4/O5 | bar: 2023 Q1
3.1 | Establishment of breeding plots for Acacia crassicarpa and Eucalyptus pellita
3.2 | Establishment of trial plots for eucalyptus hybrid, paulownia, selected elite clones of eucalyptus, and selected indigenous species.
3.3 | Conduct plot monitoring, maintenance and assessment
3.4 | Establishment of seed production area and mother tree selection for indigenous species
3.5 | Phenology monitoring and seed collection, seed processing, seed testing, seed storage trial and seed germination
3.6 | Thinning and conversion of research plot to seed production area (exotic species)
3.7 | Development of propagation method for selected plantation species
3.8 | Pest and disease surveillance and monitoring
3.9 | Research publication | bar: 2023 Q4; 2024 Q4; 2025 Q4 to 2030 Q4
3.1 | Procurement of chemical and consumables as well as laboratory equipment | bar: 2023 Q3 to 2023 Q4; 2024 Q2 to 2024 Q3; 2025 Q2 to 2025 Q3; 2026 Q1 to 2030 Q4
4 | Proposed implementation of forest landscape restoration throughout Sarawak | O3/O4/O5 | bar: 2023 Q1
4.1 | Nursery/seedling production | bar: 2023 Q1
4.1.1 | Establishment of new nursery and maintenance of existing nursery; | bar: 2023 Q1 to 2023 Q3; 2024 Q1 to 2024 Q3; 2025 Q1 to 2025 Q3
4.1.2 | Establishment of Seed Production Area, Phenology Survey, Yield Plot for high value forest tree species; | bar: 2023 Q2 to 2023 Q3; 2024 Q2 to 2024 Q3; 2025 Q2 to 2025 Q3
4.1.3 | Seeds/Wildings collection and planting material production and maintenance | bar: 2023 Q1 to 2025 Q4
4.2 | Planting
4.2.1 | Site identification and survey | bar: 2023 Q1; 2023 Q3; 2024 Q1; 2024 Q3; 2025 Q1; 2025 Q3
4.2.2 | Planting, monitoring and maintenance | bar: 2023 Q1 to 2025 Q4
4.2.3 | Strengthen collaboration for planting program with community, agencies, NGO, etc. | bar: 2023 Q1 to 2025 Q4
4.3 | Centre Of Excellence (COE) for FLR
4.3.1 | Road construction and enhance Sabal Model Forest within Sabal Forest Reserve (FR) | bar: 2023 Q1 to 2023 Q2; 2024 Q1 to 2024 Q3
4.3.2 | Feasibility study and FLR strategy for Bakam GR | bar: 2023 Q1 to 2025 Q4
4.3.3 | Upgrading work of existing Bintawa Office into FLR Resource Centre, Bintawa | bar: 2024 Q1 to 2024 Q3
4.3.4 | Other regional COE (infrastructure) | bar: 2023 Q1 to 2023 Q3; 2024 Q1 to 2024 Q3; 2025 Q1 to 2025 Q3
4.4 | Research and Development
4.5 | Promotion and Publicity
4.6 | FLR Management
4.7 | Comprehensive FLR Development Database System
5 | Development of Urban Forest Park in Kayangeran Forest Reserve, Lawas. | O5 | bar: 2023 Q1
5.1 | Land Acquisition & Siting Application process for Kayangeran URF | [33 empty] | Siting application was approved by SPA in October 2022. Land & Survey department conducted pag/boundary survey (Jun-14/9/2023) and will produce report soon. JKR to appoint consultants to conduct Topographical survey and Soil Investagation. JKR will produce plan and drawings in-house, and call for Tender before end of 2023. | bar: 2023 Q2; 2026 Q1 to 2030 Q4
5.2 | Appointment of consultant / JKR | [33 empty] | Siting application was approved in October 2022. Land & Survey department conducted pag/boundary survey (Jun-14/9/2023) and will produce report soon. JKR to appoint consultants to conduct Topographical survey and Soil Investagation. JKR will produce plan and drawings in-house, and call for Tender before end of 2023.
5.2.1 | Letter of consultant appointment / JKR | [33 empty] | Siting application was approved in October 2022. Land & Survey department conducted pag/boundary survey (Jun-14/9/2023) and will produce report soon. JKR to appoint consultants to conduct Topographical survey and Soil Investagation. JKR will produce plan and drawings in-house, and call for Tender before end of 2023. | bar: 2023 Q4
5.2.2 | Survey work / Soil Investigation | bar: 2023 Q3 to 2023 Q4
5.2.3 | Detail design/ Tender Drawing | bar: 2023 Q3 to 2023 Q4
5.2.4 | Tender Documents | bar: 2023 Q3 to 2024 Q1
5.3 | Construction Contractor appointment | bar: 2023 Q1
5.3.1 | Letter of offer | bar: 2024 Q2
5.3.2 | Letter of acceptance | bar: 2024 Q2
5.3.3 | Contract Document | bar: 2024 Q2
5.4 | Construction work at site | bar: 2024 Q3 to 2030 Q4
5.5 | Progress report | bar: 2024 Q3 to 2030 Q4
5.6 | 5.6 Project completion - (CPC, DLP, OP) | bar: 2025 Q4 to 2030 Q4
6 | Conservation and protection of wetlands and watershed within Heart of Borneo Sarawak | O3/O4/O5 | bar: 2023 Q1
6.1 | Watershed | bar: 2023 Q1
6.1.1 | Monitoring of watershed / water catchment areas within targeted licence area & PFE inundated by Baleh HEP | bar: 2023 Q1 to 2024 Q1; 2024 Q4 to 2025 Q2; 2025 Q4
6.1.2 | Forest restoration and community engagement programs | bar: 2023 Q2; 2024 Q2 to 2024 Q3; 2025 Q2 to 2025 Q3
6.1.3 | Ecosystem services studies & Assessment of Impacts | bar: 2023 Q1 to 2023 Q4; 2024 Q3 to 2025 Q1; 2025 Q3 to 2025 Q4
6.1.4 | Dialogues and awareness programs for local communities | bar: 2023 Q2 to 2023 Q4; 2024 Q2; 2024 Q4; 2025 Q2 to 2025 Q4
6.2 | Wetlands | bar: 2023 Q1
6.2.1 | Socio-economic / community needs survey at Rajang Delta | bar: 2023 Q2 to 2024 Q1; 2024 Q4 to 2025 Q2
6.2.2 | Education and capacity building for local community | bar: 2023 Q2 to 2023 Q3; 2024 Q2 to 2024 Q3; 2025 Q2 to 2025 Q3
6.2.3 | Monitoring of FR / potential Ramsar site in Rajang Delta | bar: 2023 Q2 to 2023 Q3; 2024 Q2; 2024 Q4 to 2025 Q4
6.2.4 | Sarawak Wetlands Policy Workshop | bar: 2023 Q4; 2024 Q2 to 2024 Q3; 2025 Q2 to 2025 Q3
6.2.5 | Multi-disciplinary assessment and feasibility study of Rajang Delta | bar: 2023 Q2 to 2023 Q3; 2024 Q2 to 2025 Q2
6.2.6 | Preparation of MMKN paper and proposal for Rajang Delta Ramsar Site | bar: 2025 Q1 to 2025 Q4
7 | Community support programme in Heart of Borneo | O3/O4/O5 | bar: 2023 Q1
7.1 | Implement alternative livelihood enhancement programs/activities that will alleviate poverty level.
7.2 | Capacity buildings and training.
7.3 | Infrastructure and facilities development
7.4 | Forest Landscape restoration
8 | Strengthening compliance mechanism for sustainability for post-logging block inspection | O3/O5 | bar: 2023 Q1
8.1 | Analyse operational cost on current practice (PLBI) for both licensee and government
8.2 | Identify potential job creation for community that contribute to poverty alleviation factor.
8.3 | Conduct study on verification of undersized logs that reported in Revlog versus undersized log stump counting on the ground at selected FMU area.
8.4 | Develop new mechanism in strengthening compliance for sustainability PLBI.
9 | Enhancement of community livelihood in Sarawak through social forestry programmes | O4/O5 | bar: 2023 Q1
9.1 | Development of local community non-timber forest product (NTFP) processing facilities.
9.2 | Establishment of facilities that will uplift livelihood and indirectly contribute to alleviate poverty local community.
9.3 | Conduct Communication, Education & Public Awareness (CEPA) programs with local community and scholols adjacent to PFE
9.4 | Implement Forest Landscape Restoration of NTFP planting programs involving local communities adjacent to PFE.
9.5 | Implement Agroforestry programs in Communal Forest.
10 | Quantifying Forest Carbon Stock in Sarawak | O3/O5 | bar: 2023 Q1
10.1 | Procurement of field and laboratory equipment/consumables | bar: 2024 Q1 to 2030 Q4
10.2 | Comprehensive assessment of forest biomass & carbon in selected forest areas using LiDAR, Remote sensing and ground truthing | bar: 2024 Q1 to 2030 Q4
10.3 | Consultancy for data processing, analysis and application | bar: 2024 Q1 to 2030 Q4
10.4 | Capacity building and Transfer of Technology | bar: 2024 Q1 to 2030 Q4
10.5 | Sundries (stationaries, batteries etc) | bar: 2024 Q1 to 2030 Q4
| Gain higher export earnings through the advancement in downstream processing | O1/O2/O3/O4/O5
11 | Establish furniture park in Tanjung Manis (upscale processing) | O1 | bar: 2023 Q1
11.1 | To produce blue print of Furniture Park
11.2 | To construct and establish Furniture Park in Tanjung Manis which involve two stages:
11.2.1 | Planning stage: • Identify site • Appoint consultant (to delete) • Submission to SPA and Land & Survey • To do Survey & Soil investigation • To do design • Tender | bar: 2023 Q1 to 2023 Q2
11.2.2 | Construction stage (to delete)
11.3 | To identify and confirm investors to take up the Furniture Park
11.4 | To set-up Furniture Park Management Team to manage & monitor the Furniture Park
12 | Establish bamboo plantation and develop bamboo-based industry | O1 | bar: 2023 Q1
12.1 | To develop nursery
12.2 | To establish and maintain model bamboo plantation
12.3 | To conduct stock inventory study of wild bamboo (to delete)
12.4 | To formulate policies and laws on bamboo industry
12.5 | To conduct study and establish Bamboo Plantation Certification Program
12.6 | To develop tissue culture lab
12.7 | To identify site/planters and facilitate the establishment of Commercial Bamboo Plantation
12.8 | To identify and establish Community Bamboo Farming
12.9 | To identify project management team to implement and monitor the bamboo project
13 | Utilise local plywood as one of the key components tom manufacture value added products | O1 | bar: 2023 Q1
13.1 | To review laws and policies
13.1.1 | Control of formaldehyde emission in wood products | Plywood producers comply with formaldehyde emission based on market requirement | bar: 2023 Q1
13.1.2 | Requirement of gases emission - proposed to delete
13.1.3 | Export of raw plywood | implemented sale tax ( __%)on export of raw plywood on ___ | bar: 2023 Q1
13.1.4 | Export of logs from planted forest | 100% banned of export to support local processing | bar: 2023 Q1
13.1.5 | Export of wood waste | 100% banned of export to support local processing | bar: 2023 Q1
13.1.6 | Automation in manufacturing sector | Grant for Retooling purposes was not approved | bar: 2023 Q1
13.1.7 | Importation of raw material | allow import of raw material for value added processing | bar: 2023 Q1
13.2 | To build and provide basic infrastructure required by Investors
13.2.1 | Planning Stage: • Identify Site • Appoint Consultant • Submission to SPA and Land & Survey • To do Survey & Soil Investigation • To do Design • Tender | Private sector initiative based on investor's own needs - suggest to delete
13.2.2 | Construction stage | Private sector initiative based on investor's own needs - suggest to delete
13.3 | To identify and confirm investors | ongoing
13.4 | To conduct investment promotions abroad each year | ongoing
13.5 | To set-up project management team to manage and monitor this initiative | Private sector initiative based on investor's own needs - suggest to delete
14 | Implementation of Sarawak Young Designers (SayD’signers Sarawak) programme | O1 | bar: 2023 Q1
14.1 | To engage professional to train and produce young designers (fresh graduates)
14.2 | To produce furniture designs
14.3 | To develop prototypes of the furniture designs
14.4 | To facilitate designers to participate in expo / exhibition to showcase their prototypes (Funded by STIDC)
14.5 | To obtain copyright registration of furniture designs
14.6 | To train young designers with reputable international design centres through collaboration with ITB (Institute Technology Bandung), Swinburne, Mushashino & POLI.design Milan
14.7 | To implement Incubator Program for the trained young designers
14.8 | To identify project management team to implement and monitor this initiative
15 | Establish furniture park in Kuching (upscale processing) | O1 | bar: 2023 Q1
15.1 | To produce blue print of Furniture Park
15.2 | To establish Furniture Park in Kuching:
15.2.1 | Planning Stage: • Identify Site • Appoint Consultant • Submission to SPA and Land & Survey • To do Survey & Soil Investigation • To do Design • Tender | bar: 2024 Q1 to 2024 Q4
15.2.2 | Construction stage | bar: 2025 Q1 to 2030 Q4
15.3 | To identify and confirm investors to take up the Furniture Park
15.4 | To set-up Furniture Park management team to manage & monitor the Furniture Park
16 | Research and Development for KURSI PUSAKA in UNIMAS | O1 | bar: 2023 Q1
16.1 | To enhance Terms of Reference of the UNIMAS Furniture Design Competition (Suggest to change to "Terms and Conditions of Unimas Furniture Design Competition)
16.2 | To conduct furniture design competition to select participants for SayD’Signers Sarawak Program (UNIMAS Design students) |  | 2023 Q1: annually
16.3 | To produce prototypes of Top 5 winners from the design competition |  | 2023 Q1: annually
16.4 | To fund potential relevant research by UNIMAS |  | 2023 Q3: Q3 2023 - Q3 2025
16.5 | To identify project management team to implement and monitor this initiative
17 | Pusat Latihan Perkayuan PUSAKA Tanjung Manis – Operation and maintenance grant (TMTTC) | O1 | bar: 2023 Q1
17.1 | To upgrade and maintain training facilities |  | 2023 Q1: annually
17.2 | To organise Sijil Kemahiran Malaysia (SKM) training programs & short courses |  | 2023 Q1: annually
17.3 | To collaborate with other institutes or training providers
17.4 | To identify project management team to implement & monitor this initiative
18 | Establish Sarawak Design Centre (SARADEC) | O1 | bar: 2023 Q1
18.1 | To rent a premise do renovation works
18.2 | To fully develop and manage facilities of State-of-the-Art Institution with the following facilities:
• Design studio • Model making • Prototyping • Design clinic • Galleries • Resource centre • Material lab • Co-working space / office • Incubator facilities | bar: 2023 Q1 to 2023 Q2
18.3 | Commercialisation of designs
18.4 | To collaborate with local industry, agencies & institutions
18.5 | To identify project management team to implement and monitor this initiative
19 | One-stop Inspection Centre at IQS Merapok, Lawas | O1 | bar: 2023 Q1
19.1 | To acquire land from Land & Survey for establishment of One Stop Inspection Centre at IQS Merapok, Lawas
19.2 | To appoint Consultant for design and other preliminary works
19.2.1 | Architect | bar: 2024 Q3 to 2024 Q4
19.2.2 | Civil & Structural (C&S) | bar: 2024 Q3 to 2024 Q4
19.2.3 | Mechanical & Electrical (M&E) | bar: 2024 Q3 to 2024 Q4
19.2.4 | Quantity Surveyor (QS) | bar: 2024 Q3 to 2024 Q4
19.2.5 | Survey & Soil Investigation | bar: 2024 Q3 to 2024 Q4
19.3 | To tender for construction
19.4 | To construct and complete the centre
19.5 | To manage the operation facilities
19.6 | To identify project management team to implement & monitor this initiative
20 | Proposed furniture testing laboratory | O1 | bar: 2023 Q1
20.1 | To operate and maintain furniture lab
20.2 | To collaborate with third party for lab certification
20.3 | To train staff to operate and maintain the testing lab
20.4 | To promote and provide services to furniture industry
20.5 | To identify project management team to implement and monitor this initiative
21 | Applied R&D to develop commercially viable high value products from planted timber species | O1 | bar: 2023 Q1
21.1 | To conduct research on forest plantation yield enhancement (e.g. Growth rate of forest plantation, potential of planted species, carbon trading of forest plantation, etc.)
21.2 | To conduct research on utilisation of planted timber species (e.g. Chemical properties of wood and biomass pellet from planted timber, mechanical properties of planted timber, engineered timber, etc.)
21.3 | To conduct research on utilisation of bamboo (e.g. Mechanical properties, biomass pellet, engineered bamboo, biochar, activated carbon, textile, etc.)
21.4 | To conduct applied research to support new investments (to delete)
21.5 | To identify project management team to implement and monitor this initiative
22 | Feasibility study for the proposed Megasite in Bintulu | O1 | bar: 2023 Q1
22.1 | Tendering & Selection of Consultant
22.2 | To conduct Megasite Feasibility Study
22.2.1 | On establishing integrated timber processing site within planted forest area
22.2.2 | To determine supporting enablers infrastructure for Megasite
22.3 | To submit report for consideration to implement Megasite
22.4 | To identify project management team to implement and monitor this initiative
23 | Retooling Fund of timber industry for downstream processing | O1/O2/O3/O4/O5 | bar: 2023 Q1
23.1 | To develop mechanism/criteria eligibility for providing Retooling Fund for timber industry | NO FUNDING
23.2 | Roadshow of Retooling Fund
23.3 | Implementation of retooling funding program by disbursement of fund
23.4 | Collection of repayment
23.5 | To set-up project management team to implement and monitor this initiative
| Gain national and international recognition through conservation and sustainable management | O1/O2/O3/O4/O5
24 | Establishment and Management of Forest One Stop Compliance Centre (FoSCC) and Permanent Forest Estate (PFE) | O3/O4/O5 | bar: 2023 Q1
24.1 | Identify and prioritise the FOSCC that in dire need of improvement which located within the area that generate high revenue and cater high production of timber | bar: 2023 Q1; 2024 Q1; 2025 Q1; 2026 Q1 to 2030 Q4
24.2 | Engagement with relevant agencies to assess and arrange for procurement process | bar: 2023 Q1 to 2023 Q2; 2024 Q1 to 2024 Q2; 2025 Q1 to 2025 Q2; 2026 Q1 to 2030 Q4
24.3 | Award the upgrading works to appointed contractors | bar: 2023 Q3 to 2023 Q4; 2024 Q3 to 2024 Q4; 2025 Q3 to 2030 Q4
24.4 | Monitoring and Reporting the improvement project of the FOSCC | bar: 2023 Q3 to 2023 Q4; 2024 Q3 to 2024 Q4; 2025 Q3 to 2030 Q4
24.5 | Appointment of consultant for Masterplan Study of PFE of Sarawak | bar: 2023 Q1 to 2023 Q4; 2026 Q1 to 2030 Q4
24.6 | Identify PFE that need boundary demarcation and signboard installation throughout Sarawak
24.7 | Development of Terms and Reference for PFE Masterplan | bar: 2024 Q1 to 2030 Q4
24.8 | Progress reports the Master Plan. | bar: 2024 Q1 to 2030 Q4
24.9 | Identify potential job creation for community that contribute to poverty alleviation factor.
25 | Strengthening forest enforcement through advanced technology and equipment | O3/O4/O5 | bar: 2023 Q1
25.1 | Carry out awareness programmes for local communities and stakeholders on the importance of combating illegal logging
25.2 | Identify potential job creation for local company that contribute to poverty alleviation factor
25.3 | Appointment of contractors/ suppliers and commencement of forest enforcement activities, awareness programmes and technical trainings
25.4 | Procurement of the new technology equipment for enforcement work | bar: 2023 Q1; 2024 Q1; 2025 Q1; 2026 Q1 to 2030 Q4
25.5 | Implementation, monitoring and inspection of enforcement activities
26 | Establishment of Central Depot for seized items in Sarawak | O3/O5 | bar: 2023 Q1
26.1 | Land acquisition and siting application process for Central Depot | bar: 2023 Q1 to 2023 Q4; 2026 Q1 to 2030 Q4
26.2 | Appointment of consultant / JKR
26.2.1 | Letter of Appointment for consultant / JKR | bar: 2023 Q2; 2026 Q1 to 2030 Q4
26.2.2 | Survey work / soil investigation | bar: 2023 Q4; 2026 Q1 to 2030 Q4
26.2.3 | Detail design/ tender drawing | bar: 2023 Q4 to 2024 Q1; 2026 Q1 to 2030 Q4
26.2.4 | Tender documents | bar: 2024 Q1 to 2024 Q2; 2026 Q1 to 2030 Q4
26.3 | Contractor appointment
26.3.1 | Letter of Appointment | bar: 2024 Q3; 2026 Q1 to 2030 Q4
26.3.2 | Letter of Acceptance | bar: 2024 Q3; 2026 Q1 to 2030 Q4
26.3.3 | Contract document | bar: 2024 Q3; 2026 Q1 to 2030 Q4
26.4 | Construction work at site | bar: 2024 Q4 to 2030 Q4
26.5 | Progress report | bar: 2024 Q4 to 2030 Q4
26.6 | Project Completion - (CPC, DLP, OP) | bar: 2025 Q4 to 2030 Q4
26.7 | Identify potential job creation for community that contribute to poverty alleviation factor. | bar: 2024 Q4 to 2030 Q4
27 | Artificial Intelligence (AI) and Forensic Timber Identification for forest protection and revenue generation | O3/O5 | bar: 2023 Q1
27.1 | Development and deployment of field-deployable Sarawak Wood ID App through smartphones using AI platform for 50 Sarawak’s timber group
27.2 | Impart on legal framework that will enforce all FTL to subscribe to the wood timber ID apps in compliance for legality requirements along the Chain of Custody (CoC) and impart legal framework to collect fees from the subscription of the apps for each wood ID. | bar: 2025 Q1 to 2030 Q4
27.3 | Appointment of AI timber model building service platform developer to develop, maintain and upgrade AI models for Sarawak timber groups
27.4 | Establishment of strategic collaboration through MOU/MOA with national/internationally renowned institutions and/or universities in the field of forensic timber DNA | bar: 2024 Q2; 2026 Q1 to 2030 Q4
27.5 | Implement capacity building programmes: E.g. training, study visit, seminar and conference/ publication
27.6 | Stakeholders engagement through Training and familiarisation in the application of the wood ID app for enforcement officers throughout Sarawak (FDS, STIDC and Custom | bar: 2025 Q4 to 2030 Q4
27.7 | Forensic Timber DNA: Developing DNA barcode reference library of commonly traded timber as well protected species of Sarawak and CITES | bar: 2024 Q3 to 2030 Q4
27.8 | Digitalisation of Sarawak’s wood library (Xylarium) as well upgrading of the Xylarium , anatomy and chemistry laboratory | bar: 2024 Q2 to 2030 Q4
28 | Development of Sustainable Forest Management (SFM) Centre in Central Region, Sarawak | O3/O5 | bar: 2023 Q1
28.1 | Land acquisition and siting application process for SFM Centre | bar: 2023 Q1 to 2023 Q4; 2026 Q1 to 2030 Q4
28.2 | Appointment of consultant / JKR
28.2.1 | Letter of Appointment for consultant / JKR | bar: 2023 Q2
28.2.2 | Survey work / soil investigation | bar: 2023 Q4
28.2.3 | Detail design/ tender drawing | bar: 2023 Q4 to 2024 Q1
28.2.4 | Tender documents | bar: 2024 Q1 to 2024 Q2
28.3 | Contractor appointment
28.3.1 | Letter of Appointment | bar: 2024 Q3
28.3.2 | Letter of Acceptance | bar: 2024 Q3
28.3.3 | Contract document | bar: 2024 Q3
28.4 | Construction work at site | bar: 2024 Q4 to 2030 Q4
28.5 | Progress report | bar: 2024 Q4 to 2030 Q4
28.6 | Project Completion - (CPC, DLP, OP) | bar: 2025 Q4 to 2030 Q4
28.7 | Identify potential job creation for community that contribute to poverty alleviation factor. | bar: 2024 Q4 to 2030 Q4
29 | Integrated forest ecological study for resource utilisation and management | O3/O4/O5 | bar: 2023 Q1
29.1 | Undertake tissue culture research for selected non-timber species
29.2 | Data collection and nursery raising for potential plant species to propagate
29.3 | Extensive inventory surveys on forest biological resources and environment
29.4 | Identify potential job creation by engaging qualify contract workers
29.5 | Conduct training for the staffs and contract workers on field inventory works including sampling and data analysis, database entry, and micropropagation method.
29.6 | Conduct inventory surveying within the identified Permanent Forest Estates (PFEs)
29.7 | Intensive data entry into the developed database system, scanning specimen into digital image
29.8 | Undertake tissue culture research for selected non-timber species
29.9 | Undertake tissue culture research for selected endangered species
30 | Anthropogenic effects to forest conservation and ecosystem sustainability | O3/O4/O5 | bar: 2023 Q1
30.1 | Identify potential ecotourism conservation area
30.2 | Create job from research and eco-tourism activities such as homestay, transportation, local guide and porters
30.3 | Raise awareness on anthropogenic activities and encourage strengthening the role of forests.
30.4 | Conduct intensive research and monitoring
30.5 | Conduct in-situ and ex-situ conservation efforts
30.6 | Compile baseline data based on research assessment/findings.
31 | Assessment on habitat of fauna in PFE in support of Forest Management Certification (FMC) | O3/O4/O5 | bar: 2023 Q1
31.1 | Implement conservation program within production area
31.2 | Conduct research on the difference between Impacts of conventional logging and RIL
31.3 | Conduct awareness program on wildlife to stakeholders and local communities
31.4 | Capacity building program with stakeholders and local communities
31.5 | Identify potential job creation for local community
31.6 | Conduct research of Impacts of logging activities towards wildlife population in FMU area.
32 | Sarawak Delta Geopark | O4/O5 | bar: 2023 Q1
32.1 | Administration and management of SDGp
32.2 | Development programs, public awareness and promotion
32.3 | Provision of basic infrastructure
32.4 | Preparation of development plan and strategic management
32.5 | Research and development
32.6 | Capacity development
33 | Achieve world class recognition for biodiversity conservation and protected areas management | O1/O2/O3/O4/O5 | bar: 2023 Q1
33.1 | Inscription of Niah NP as UNESCO-World Heritage Site (WHS) | 02/05
33.1.1 | Appointment of consultant
33.1.2 | Preparation of Tentative List
33.1.3 | Preparation of nomination dossier
33.1.4 | Writing and submission of dossier
33.1.5 | Evaluation and nomination of Niah NP as WHS | bar: 2023 Q1 to 2026 Q4
33.1.6 | Development of Infrastructure and facilities | bar: 2023 Q1 to 2027 Q4
• Identify site, • Appointment of consultant • Site survey and investigation, • Site Plan and schematic design • Application of siting and building plan approval by SPA and SBDC (where applicable) • Detail plan and tender documentation • Tendering and evaluation • Tender award and construction
33.2 | Lambir Hills NP and Bako NP as ASEAN Heritage Park (AHP) | 02/05
33.2.1 | Intention to nominate | bar: 2023 Q3 to 2024 Q1
33.2.2 | Proposal on AHP action plan | bar: 2023 Q4 to 2024 Q1
33.2.3 | Appointment of consultants | bar: 2024 Q1
33.2.4 | Preparation of management plans and nomination documents | bar: 2024 Q1 to 2024 Q4
33.2.5 | Endorsement of nomination documents (ACB National Contact Point ie KeTSA) | * NRECC requires 2-3 months timeline for review & endorsement (parliment & submission of dossier to AHP) Beyond SFC / Under purview of ASEAN Centre for Biodiversity (ACB) | bar: 2024 Q4 to 2025 Q1
33.2.6 | Review and endorsement of nomination documents – conduct of desk review and field evaluation | bar: 2025 Q1 to 2025 Q2
33.2.7 | Review and endorsement of nomination documents | bar: 2025 Q3 to 2025 Q4
33.2.8 | Endorsement of nomination documents | bar: 2025 Q3 to 2025 Q4
33.2.9 | Approval of nominations | bar: 2025 Q3 to 2025 Q4
33.3 | Inscription of Kuala Lawas/Kuala Trusan & Limbang Mangrove NP as East Asia-Australian Flyway Network site | 02/05
33.3.1 | Preparation of Site Information Sheet (SIS) | bar: 2023 Q1 to 2025 Q4
33.3.2 | Endorsement of SIS | bar: 2026 Q1 to 2030 Q4
33.3.3 | Preparation of Management Plans | bar: 2023 Q1 to 2024 Q4
33.4 | Inscription of Danau Mujan NP and Loagan Bunut NP as RAMSAR Sites | 02/05
33.4.1 | Intention to nominate | bar: 2023 Q3 to 2023 Q4; 2027 Q3 to 2027 Q4
33.4.2 | Consultation with stakeholders on proposed nomination | bar: 2024 Q1 to 2024 Q2; 2027 Q1 to 2027 Q2
33.4.3 | Develop supporting nomination document | bar: 2024 Q3 to 2025 Q2; 2026 Q1 to 2026 Q4
33.4.4 | Jurisdiction endorsement and submission of formal nomination | * NRECC requires 2-3 months timeline for review, presentation & endorsement by parliment | bar: 2025 Q2 to 2025 Q3; 2028 Q1 to 2028 Q2
33.4.5 | Formal review of Ramsar nomination | bar: 2025 Q2 to 2025 Q3; 2028 Q3 to 2028 Q4
33.4.6 | Ramsar Site designation | bar: 2025 Q4; 2029 Q1 to 2029 Q2
33.5 | To certify 20 sites under IUCN Green List of Protected and Conserved Areas | 02/05
33.5.1 | Preparation and submission of evidence for five indicators for completion of Application Phase | [33 empty] | 2023 - Gunung Buda NP & Gunung Lesong NP
33.5.2 | Preparation and submission of evidence supporting forty-five indicators for completion of Candidate Phase | [33 empty] | 2023 - Bako NP & Santubong NP
33.5.3 | Site visit and evaluation by assessor | bar: 2026 Q4; 2027 Q4; 2028 Q4; 2029 Q4; 2030 Q4
33.5.4 | Green List designation | Note: Beyond SFC/ Under purview of IUCN Green List
33.6 | Conduct periodical assessment to maintain recognition status. Note: Oly applicable after inscription | 02/05
33.7 | Identify potential TPA to be managed by managing agent | 05
33.8 | Review gazetted fee for TPA | 02/05
33.9 | Identify community development /participation program | 02
34 | Management and strengthening protection for selected Totally Protected Areas (TPAs) | O1/O2/O3/O4/O5 | bar: 2023 Q1
34.1 | Securing TPA integrity through cadastral perimeter survey of boundaries
34.1.1 | Appointment of chartered surveyors from Board of Survey | bar: 2023 Q1 to 2027 Q4
34.1.2 | Stakeholders engagement | bar: 2023 Q1 to 2028 Q1
34.1.3 | Field boundary survey (Chartered surveyors) | bar: 2023 Q2 to 2028 Q3
34.1.4 | Cadastral map | Note: Beyond SFC / Approval under the purview of L&S
34.2 | Securing TPA integrity through cadastral perimeter survey of boundaries | 02/05
34.2.1 | Appointment of chartered surveyors from Board of Survey | bar: 2024 Q1 to 2029 Q4
34.2.2 | Stakeholders engagement | bar: 2024 Q1 to 2030 Q1
34.2.3 | Field boundary survey (Chartered surveyors) | bar: 2024 Q1 to 2030 Q3
34.2.4 | Cadastral map | Note: Beyond SFC / Approval under the purview of L&S
34.3 | Prepare Management plans for 4 TPAs: | 02/05
34.3.1 | Bako NP by 2023 | bar: 2023 Q1 to 2023 Q4
34.3.2 | Lambir Hills NP by 2024 | bar: 2023 Q1 to 2023 Q4
34.3.3 | Limbang Mangroves NP by 2026 | bar: 2023 Q1 to 2023 Q4
34.3.4 | Kuala Lawas NP by 2026 | bar: 2023 Q1 to 2024 Q4
6.13a.1 6.13b.1 | Formulation of Mgt Plan for TPAs (new & review/ update existing) - 23 TPAs Note: Limbang Mangrove, Bako & Lambir Hills already captured under 32.2
• Appointment of consultants • Stakeholders engagement • Field inventory and social survey • Management Plans
34.4 | Identify services / work / program for community participation in managing and protecting TPA | 02
35 | Development and upgrading of integrated facilities at 20 Totally Protected Areas (TPAs) | O1/O2/O3/O4/O5 | bar: 2023 Q1
35.1 | To develop and upgrade facilities at selected manned and unmanned TPAs: | 02/05
35.1.1 | Matang Wildlife Centre | bar: 2023 Q1 to 2026 Q2
35.1.2 | Kubah National Park | bar: 2023 Q1 to 2026 Q4
35.1.3 | Pulau Talang Besar & Tanjung Datu National Park | bar: 2025 Q3 to 2029 Q4
35.1.4 | Maludam National Park | bar: 2023 Q1 to 2026 Q2
35.1.5 | Loagan Bunut National Park | bar: 2023 Q1 to 2026 Q2
35.1.6 | Gunung Lesong National Park | bar: 2023 Q1 to 2028 Q4
35.1.7 | Kuching Wetland National Park | bar: 2023 Q1 to 2026 Q2
35.1.8 | Gunung Apeng National Park | bar: 2023 Q1 to 2025 Q3
35.1.9 | Gunung Buda National Park | bar: 2025 Q3 to 2028 Q4
35.1.10 | Batang Ai National Park | bar: 2023 Q1 to 2028 Q4
35.1.11 | Bukit Lima Nature Reserves | bar: 2023 Q1 to 2026 Q3
35.1.12 | Samunsam Wildlife Sanctuary | bar: 2025 Q3 to 2028 Q4
35.1.13 | Rajang Mangrove National Park | bar: 2025 Q3 to 2029 Q2
35.1.14 | Limbang Mangrove National Park | bar: 2025 Q3 to 2029 Q3
35.1.15 | Usun Apau National Park | bar: 2025 Q3 to 2029 Q3
35.1.16 | Sabal National Park | bar: 2025 Q3 to 2028 Q4
35.1.17 | Danau Mujan National Park | bar: 2025 Q3 to 2029 Q3
35.1.18 | Baleh National Park | bar: 2025 Q3 to 2029 Q4
35.1.19 | Ulu Sebuyau National Park | bar: 2025 Q3 to 2029 Q4
35.1.20 | Sedilu National Park | bar: 2025 Q3 to 2029 Q4
• Secure funding • Identify site • Appointment of consultant / assign technical team for In-house project • Site survey and investigation • Site Plan and schematic design • Application of siting and building plan approval by SPA and SBDC • Detail plan and tender documentation • Tendering and evaluation • Tender award and construction
35.2 | Identify work that can be outsource to the local community | 02 | bar: 2023 Q1 to 2028 Q4
36 | Integrated wildlife conservation and management in Sarawak | O1/O2/O3/O4/O5 | bar: 2023 Q1
36.1 | To establish a comprehensive database on flora and fauna inside TPAs in Sarawak for effective management. Action steps: | 02/05
36.1.1 | Establish TORs for site selection.
36.1.2 | Identify the areas (TPAs) based on TORs (target – 17 TPAs)
36.1.3 | Prepare project proposals (e.g. literatures review)
36.1.4 | Identify budget source and others requirement (e.g. equipment, manpower, logistics, etc.) | bar: 2023 Q1 to 2029 Q4
36.1.5 | Apply research permit from state government through SORAS system (if necessary)
36.1.6 | Project proposal approved
36.1.7 | Project implementation and monitoring (field assessment, stakeholders consultation, etc.)
36.1.8 | Reporting (field report, publications or book)
36.1.9 | Organise workshop / seminar | bar: 2025 Q1 to 2025 Q4; 2030 Q1 to 2030 Q4
36.2 | To establish a comprehensive database on flora and fauna outside TPAs in Sarawak for future planning. Action steps: | 02/05
36.2.1 | Establish TORs for site selection. | bar: 2023 Q1 to 2023 Q4
36.2.2 | Identify the areas / habitats outside or adjacent to existing TPAS based on TORs. | bar: 2023 Q1 to 2024 Q4
36.2.3 | Stakeholders engagement (organise dialogue with DO, local communities and others relevant agencies)
36.2.4 | Prepare project proposals (e.g. literatures review)
36.2.5 | Identify budget source and others requirement (e.g. equipment, manpower, logistics, etc.)
36.2.6 | For research activities, research permit from state government is required through SORAS system.
36.2.7 | Project proposal approved
36.2.8 | Project implementation and monitoring (field assessment, stakeholders consultation, etc.)
36.2.9 | Reporting (field report, publications or book)
36.2.10 | Organize workshop or seminar | bar: 2025 Q1 to 2025 Q4; 2030 Q1 to 2030 Q4
36.3 | To produce Sarawak Red list (for terrestrial and Marine) mammals. Action steps: | 02/05
36.3.1 | Prepare red list proposal or framework. | bar: 2024 Q1 to 2024 Q4
36.3.2 | Identify key stakeholders or collaborators (e.g. Government agencies, local or foreign University, NGO, etc.) for long-term monitoring for threatened and rare flora and fauna species | bar: 2024 Q1 to 2030 Q4
36.3.3 | Identify budget source and others requirement (e.g. equipment, manpower, logistics, etc.) | bar: 2024 Q1 to 2030 Q4
36.3.4 | Apply research permit from state government through SORAS system (if any research activities involve) | bar: 2024 Q1 to 2030 Q4
36.3.5 | Field assessment and collection of data. | bar: 2024 Q1 to 2030 Q4
36.3.6 | Organise workshop / seminar | bar: 2025 Q1 to 2025 Q4; 2030 Q1 to 2030 Q4
36.4 | To restore degraded areas in TPAs in line with state government policy. Action steps: | 02/05
36.4.1 | Identify the areas / habitats (e.g. rapid assessment)
36.4.2 | Stakeholders engagement (organise dialogue with DO, local communities and others relevant agencies)
36.4.3 | Establish restoration framework
36.4.4 | Identify budget source and others requirement (e.g. Planting materials, equipment, manpower, logistics, etc.)
36.4.5 | Project implementation and monitoring (field assessment, etc.)
36.4.6 | Reporting (field report, publications or book)
36.4.7 | Organise workshop or seminar
36.5 | To renovate and/or reconstruct where necessary research field station facilities, Landeh (ex-situ conservation facilities), & field station at Ng Segerak, Ng Bloh & Ng Ju. Actions steps: | 02/05
36.5.1 | Field station | [33 empty] | To apply for new funding under 13MP (scope completion subject to 13MP approval) . | bar: 2026 Q1 to 2026 Q4
36.5.2 | Site inspection | bar: 2026 Q1 to 2026 Q4
36.5.3 | Estimate construction cost | bar: 2026 Q1 to 2026 Q4; 2028 Q1 to 2028 Q4; 2030 Q1 to 2030 Q4
36.5.4 | Engage with local community to do the reconstruction work | bar: 2026 Q1 to 2030 Q4
36.5.5 | Repair, maintenance or enhancing implemented according. | bar: 2026 Q1 to 2030 Q4
36.5.6 | Work verification and endorsement by implementing agency | bar: 2030 Q1 to 2030 Q4
36.6 | Conducting capacity building for staff participating in the project. Action steps: | 02/05
36.6.1 | Training needs analysis | bar: 2024 Q1 to 2024 Q4; 2027 Q1 to 2027 Q4; 2030 Q1 to 2030 Q4
36.6.2 | Identify training needs | bar: 2024 Q1 to 2024 Q4; 2027 Q1 to 2027 Q4; 2030 Q1 to 2030 Q4
36.6.3 | Selection of relevant staff | bar: 2024 Q1 to 2024 Q4; 2027 Q1 to 2027 Q4; 2030 Q1 to 2030 Q4
36.6.4 | Identify training providers & consultants and trainers | bar: 2025 Q1 to 2030 Q4
36.6.5 | Training evaluation | bar: 2025 Q1 to 2030 Q4
36.6.6 | Reporting | bar: 2025 Q1 to 2030 Q4
36.7 | Produce brochures, pamphlets, publications, or books | 02/05
36.8 | Identify programme for community development and participation in managing wildlife | 02/05
37 | Rural transformation through community participation in biodiversity conservation and protected areas management services | O1/O2/O3/O4/O5 | bar: 2023 Q1
37.1 | Implementation of community based economic programs | 02/05
37.1.1 | Identify areas
37.1.2 | Gathering background information
37.1.3 | Project Planning
37.1.4 | Project Implementation
37.1.5 | Evaluation and monitoring | bar: 2024 Q1 to 2030 Q4
37.2 | Implementation of Community engagement programs by engaging community participation in Biodiversity Conservation Projects | 02
37.2.1 | Gathering background information
37.2.2 | Project Planning
37.2.3 | Project implementation & maintenance, monitoring
37.2.4 | Project maintenance & monitoring | bar: 2024 Q1 to 2030 Q4
37.3 | Implementation of Community engagement programs by engaging community participation in Biodiversity Conservation Projects | 02
37.3.1 | Gathering background information
37.3.2 | Project Planning
37.3.3 | Project implementation
37.3.4 | Evaluate and monitor
38 | Establishment of wildlife rescue centre & forensics laboratory | O1/O2/O3/O4/O5 | bar: 2023 Q1
38.1 | Establishment Of Wildlife Conservation And Rescue Centre | 02/05
38.1.1 | Field station | [33 empty] | To apply for new funding under 13MP (scope completion subject to 13MP approval) . | bar: 2026 Q1 to 2026 Q4
38.1.2 | Site inspection | bar: 2026 Q1 to 2026 Q4
38.1.3 | Appointment of consultant to do estimation cost and to produce schematic drawing / plan. | bar: 2026 Q1 to 2027 Q4
38.1.4 | Estimation cost and schematic plan approved by Jawatan Kuasa technical. | bar: 2026 Q1 to 2027 Q4
38.1.5 | Prepare tender documents | bar: 2026 Q1 to 2027 Q4
38.1.6 | Tender advertisement | bar: 2026 Q1 to 2027 Q4
38.1.7 | Tender evaluation and selection of contractor. | bar: 2026 Q1 to 2027 Q4
38.1.8 | Commencement of work | bar: 2028 Q1 to 2030 Q4
38.1.9 | Work verification and endorsement by implementing agency | bar: 2030 Q1 to 2030 Q4
38.2 | Capacity Building especially in animal handling and husbandry | 02/05
38.2.1 | Training needs analysis | bar: 2026 Q1 to 2026 Q4; 2029 Q2 to 2030 Q1
38.2.2 | Identify training needs | bar: 2026 Q1 to 2026 Q4; 2029 Q2 to 2030 Q1
38.2.3 | Selection of relevant staff | bar: 2026 Q1 to 2026 Q4; 2029 Q2 to 2030 Q1
38.2.4 | Identify training providers & consultants and trainers | bar: 2026 Q1 to 2026 Q4; 2029 Q2 to 2030 Q1
38.2.5 | Training evaluation | bar: 2027 Q1 to 2030 Q4
38.2.6 | Reporting | bar: 2027 Q1 to 2030 Q4
38.3 | Develop TOR or SOPs for wildlife enclosures setup to facilitate seized life exhibits handlings | 05
38.3.1 | Prepare TOR or SOPs | bar: 2026 Q1 to 2026 Q4
38.3.2 | TOR or SOPs approved | bar: 2026 Q1 to 2026 Q4
38.3.3 | Implementation of SOPs | bar: 2027 Q1 to 2030 Q4
38.4 | Establishment of wildlife forensic laboratory | 02/05
38.4.1 | Site inspection | bar: 2026 Q1 to 2030 Q4
38.4.2 | Appointment of consultant to do estimation cost and to produce schematic drawing / plan. | bar: 2026 Q1 to 2030 Q4
38.4.3 | Estimation cost and schematic plan approved by Jawatan Kuasa technical. | bar: 2026 Q1 to 2030 Q4
38.4.4 | Prepared tender documents | bar: 2026 Q1 to 2030 Q4
38.4.5 | Tender advertisement | bar: 2026 Q1 to 2030 Q4
38.4.6 | Tender evaluation and selection of contractor. | bar: 2026 Q1 to 2030 Q4
38.4.7 | Commencement of work | bar: 2026 Q1 to 2030 Q4
38.4.8 | Work verification and endorsement by implementing agency | bar: 2026 Q1 to 2030 Q4
38.5 | Establishment digital gene-bank for Sarawak’s Biodiversity and equipment | 02/05
38.5.1 | Collection of samples | [33 empty] | Currently supported by RMK12 but completion subject to RMK-13 funding approval)
38.5.2 | Analyses of samples
38.5.3 | Compilation of data
38.5.4 | Populate data
38.6 | Capacity Building | 02/05
38.6.1 | Training needs analysis | [33 empty] | Currently supported by RMK12 but completion subject to RMK-13 funding approval) | bar: 2023 Q1 to 2027 Q1
38.6.2 | CSI | bar: 2024 Q1 to 2030 Q4
38.6.3 | Lab analysis | bar: 2024 Q1 to 2030 Q4
38.6.4 | PELTS training | bar: 2024 Q1 to 2030 Q4
38.6.5 | Selection of relevant staff | bar: 2023 Q1 to 2027 Q1
38.6.6 | Identify training providers & consultants and trainers
38.6.7 | Training evaluation | bar: 2024 Q1 to 2030 Q4
38.6.8 | Reporting | bar: 2025 Q1 to 2030 Q4
38.7 | Identify work that can be monetised | 02/05
39 | Establishment of Rainforest / Nature Discovery Centre (Semenggoh Rainforest Discovery Centre (SRDC) and Nature Discovery Centre, Piasau Nature Reserve) | O1/O2/O3/O4/O5
39.1 | To establish Rainforest Discovery Centre at Semenggoh | 02/05
39.1.1 | Identify site
39.1.2 | Appointment of consultant
39.1.3 | Site survey and investigation
39.1.4 | Development of overall Master Plan, site layout and schematic design for Phase 1, 2 and 3
39.1.5 | Application of siting and building plan approval by SPA and SBDC (where applicable)
39.2 | Development of Phase 1: Wildlife Centre Zone of SRDC | 02/05
39.2.1 | Detail plan and tender documentation | bar: 2023 Q1 to 2023 Q4
39.2.2 | Tendering and evaluation for Phase 1 | bar: 2023 Q3 to 2024 Q2
39.2.3 | Tender award and construction | bar: 2023 Q4 to 2027 Q2
39.3 | Development of Phase 2: Entrance Zone SRDC | 02/05
39.3.1 | Secure funding | bar: 2025 Q1 to 2025 Q4
39.3.2 | Detail plan and tender documentation | bar: 2026 Q2 to 2026 Q4
39.3.3 | Tendering and evaluation for Phase 2 | bar: 2026 Q3 to 2026 Q4
39.3.4 | Tender award and construction | bar: 2026 Q4 to 2029 Q4
39.4 | Development of Phase 3: Botanical Zone of SRDC | 02/05
39.4.1 | Secure funding | bar: 2025 Q1 to 2025 Q4
39.4.2 | Detail plan and tender documentation | bar: 2026 Q2 to 2026 Q4
39.4.3 | Tendering and evaluation for Phase 3 | bar: 2026 Q3 to 2026 Q4
39.4.4 | Tender award and construction | bar: 2026 Q4 to 2029 Q4
39.5 | To establish Nature Discovery Centre Piasau: Phase 1: | 02/05
39.5.1 | Appointment of consultant for Feasibility study | bar: 2023 Q3 to 2023 Q4
39.5.2 | Survey and investigation on Social economic, aquatic tourism potential, facilities required, site and environmental assessment, etc. | bar: 2023 Q3 to 2024 Q1
39.6 | To establish Nature Discovery Centre Piasau: Phase 2: | 02/05
39.6.1 | Secure funding
39.6.2 | Identify site
39.6.3 | Appointment of consultant | bar: 2023 Q3 to 2023 Q4
39.6.4 | Site survey and investigation | bar: 2023 Q3 to 2024 Q1
39.6.5 | Development of overall Master Plan, site layout and schematic design | bar: 2023 Q3 to 2024 Q1
39.6.6 | Application of siting and building plan approval by SPA and SBDC (where applicable) | bar: 2023 Q4 to 2024 Q1
39.6.7 | Detail plan and tender documentation | bar: 2023 Q4 to 2024 Q2
39.6.8 | Tendering and evaluation | bar: 2024 Q2
39.6.9 | Tender award and construction | bar: 2024 Q2 to 2028 Q4
39.7 | Identify community development / participation program | 02 | bar: 2025 Q1 to 2027 Q4
Legend:
Completed
Actual Plan

## 2024 Dashboard Worksheet
DASHBOARD WORKSHEET (EXISTING)
No. | OUTCOME KPIS (as stated in PCDS 2030 Summary) | 2030 Target | 2023 | 2024 | 2025
1 | Increase Timber & Non Wood Forest Products Exports Earnings | Annual Export Value of RM8 billion by 2030 | RM4 Billion (annually) | RM4 Billion (annually) | RM4 Billion (annually)
2 | Community-Based Ecotourism and conservation Totally Protected Area | 50 | 53 (annually) | 26 (annually) | 33 (annually)
3 | Certify Long Term Forest License Area and Forest Plantation | -3.0 mill ha (natural forest) -178,000 ha forest plantation (100%) | 60% (FMU) = 1.8mil ha 55%(FPMU) = 97.9k ha *cumulative | 80% (FMU) = 2.4mil ha 75%(FPMU) = 133.5k ha *cumulative | 100% (FMU) = 3.0 mil ha 100%(FPMU) = 178k ha *cumulative
No. | OUTCOME KPIS (Revised by Ministry) | 2030 Target | 2023 | 2024 | 2025
4 | 200,000 ha degraded area (100%) planted/restored by 2030 Note: Current restored area (2020-2022) = 52,555.89 ha (26.28%) 2023 - 33,472.80 ha 2024 - 21,028.90 as at June 2024 | 200,000 ha degraded area (100%) planted/restored | 10% area planted/restored = 20,000 ha *annually | 10% area planted/restored = 20,000 ha *annually | 10% area planted/restored = 20,000 ha *annually
5 | Obtain world recognition for sustainable management practices and conservation effort | 6 Recognition: -UNESCO World Heritage Site; -UNESCO Global Geopark; -ASEAN Heritage Park; -IUCN Greenlist; -East Asia- Australian Flyway Network Site; and -RAMSAR | Sarawak Delta Geopark (SDGp) -Preparation of SDGp management plan. >Commencement of Study on SDGp Development and Management Plan 2040. >Producing Interim Report of Study by end of 2023. -Preparation of application dossier -Engagement with national expert group -Increase visibility through signage and information panels -Initiate SDGp website -Produce promotional materials for SDSGp initiative such as bulletin, coffee table books and corporate video -Completion of upgrading of Gallery in Damai Central | Level of readiness is achieved. -SDGp will submit nomination for UNESCO Global Geopark in 2025 for evaluation. -Completion of DGp Development and Management Plan 2040 in Q1 2024. -Stakeholders workshop -Preparation of self-evaluation document -Completion of SDGp Website -Organise International Seminar -Completion of Dossier -Revisit Geosites -Improve information panels -Readiness assessment by JK Pelaksana Geopark Kebangsaan -Submission of letter of intent (before 1 July) -Submission of application dossier (1 Oct -30 Nov) | SDGp adhere all the requirements for belonging to the Global Geoparks Network -Preparation for evaluation -Desktop assessment by Unesco Global Geopark Panel -Field evaluation by evaluation missions Implementing the programs and plans as recommended in the SDGp management plan.
|  |  | Niah National Park as UNESCO World Heritage Site (WHS) Submission of nomination dossier Preparation for assessment by ICOMOS Assessment/Evaluation of Niah NP by ICOMOS. | Niah NP successfully inscribed as a WHS. *Streamlining the protection and management of Niah NP with the Operational Guidelines for the Implementation of the World Heritage Convention Note: In the event inscription is unsuccessful, there will be another level of improvement of the property that needs to be done to fulfil the inscription requirement e.g. Management of the conservation/ archaeological sites etc. | Niah NP successfully inscribed as a WHS. *Streamlining the protection and management of Niah NP with the Operational Guidelines for the Implementation of the World Heritage Convention Note: In the event inscription is unsuccessful to follow through all Management plans accordingly to ensure that the property is managed and developed sustainably.
No. | INITIATIVE MILESTONES | Impacting which outcome | Measure | Q1 2024 Target | Q2 2024 Target | Q3 2024 Target | Q4 2024 Target
1 | Bamboo Industry Development - To develop nurseries to produce 4,000,000 bamboo seedling by 2030 - To establish 10,000 ha of bamboo plantation by 2030 | Outcome 1 | Poject milestone & deliverables achieved | To produce 162,500 seedlings To plant 375 ha of bamboo | To produce 325,000 seedlings To plant 750 ha of bamboo | To produce 487,500 seedlings To plant 1,125 ha of bamboo | To produce 650,000 seedlings To plant 1,500 ha of bamboo
2 | Furniture Park - Kuching - Tanjong Manis | Outcome 1 | Poject milestone & deliverables achieved | 1. Siting Approval 2. Submission of SDEC Paper | To acquire fund | Appointment of consultant, design, survey and soil investigation | Completion of design, survey and soil investigation.
3 | Proposed Implementation of Forest Landscape Restoration Throughout Sarawak | Outcome 2, Outcome 1 Outcome 4 | Project action steps and planned output achieved | 1. Identification of potential FLR area inside PFE throughout Sarawak | (on-going works to achieve Q3 2024 target) | 1. 3 Seed Production Area established 2. 1 FLR Conference/seminar/ workshop conducted | 1. 7 million trees planted (20,000ha area) 2. 20 planting program/collaborations 3. 120 jobs created 4. 2 R&D related to FLR conducted. 5. 100% planting data updated in Penghijauan Malaysia
4 | Conservation and Protection of Wetlands and Watershed Within Heart of Borneo Sarawak (HoB) | Outcome 2, Outcome 5 | Project action steps and planned output achieved | 1. Workshop of assessent Wetland area for Ramsar Site 2. Multi-disciplinary assessment and feasibility study of Kuala Rajang 3. Engagement with communities in Wetland area, Sarikei 4. Preparation for appoitment of consultant (Multi-disciplinary assessment and feasibility study of Kuala Rajang) | 1. Communities Development Program in Watershed area, Baleh 2. Organize Program of Communication, Education & Public Awareness (CEPA) in Wetland area, Sarikei | 1. Appoitment of consultant to conduct Multi-disciplinary assessment and feasibility study of Kuala Rajang (Biodiversity study) 2. Program of Communication, Education & Public Awareness (CEPA) in Watershed area, Baleh 3. Communities Development Program in Wetland area, Sarikei | 1. Workshop to prepare Proposal of Ramsar site 2. Annual Workshop of Wetland and Watershed involving stakeholders and communities
5 | Strengthening Forest Enforcement Through Advancing the Technology and Equipments | Outcome 3 | Project action steps and planned output achieved | 1. Prepare & process tender document (rental of land & river transportation for forest enforcement activities at Kapit, Sibu, Sarikei, Bintulu, Miri & Limbang Region) 2. Appointment of tenderer for tender (rental of land & river transportation for forest enforcement activities at Kapit, Sibu, Sarikei, Bintulu, Miri & Limbang Region) 3. Implementation of forest enforcement activities 4. Workshop on Awareness Programme (Forest Enforcement) 5. Awareness Program (Forest Enforcement) – 1 programme 6. Prepare document on Forest Training (Technical training for forest enforcement officers) 7. Technical training for forest enforcement officers – 1 program | 1. Implementation of forest enforcement activities – 3 Operasi Rengas Bersepadu (combating Illegal logging) 2. Awareness Program (Forest Enforcement) – 3 programmes 3. Technical training for forest enforcement officers – 2 programmes | 1. Implementation of forest enforcement activities – 4 Operasi Rengas Bersepadu (combating Illegal logging) 2. Awareness Program (Forest Enforcement) – 3 programmes 3. Technical training for forest enforcement officers – 1 programmes | 1. Implementation of forest enforcement activities – 2 Operasi Rengas Bersepadu (combating Illegal logging) 2. Awareness Program (Forest Enforcement) – 2 programmes 3. Technical training for forest enforcement officers – 1 programmes
6 | Management and strengthening protection for selected Totally Protected Areas 1. Securing TPA Integrity through cadastral perimeter survey of boundaries (27 NPs) 2. TPA Management Plans developed (4 NPs) Note: Under Tourism Sector No. 6.13a: TPA-Mgt Plans integrated with Tourism MP renewed (12 NPs) No. 6.13b: New TPA Mgt Plans with Tourism MP incorporated (11 NPs) | Outcome 2, Outcome 5 | Poject milestone & deliverables achieved | A. CADASTRAL SURVEY 1. Appointment of consultant for Loagan Bunut NP Cadastral survey 2. 50% Completion of Sabal NP cadastral survey B. MANAGEMENT PLANS 1. Limbang Mangrove NP/ Kuching Wetland NP/ Wind Cave NR/ Fairy Cave NR/ Semenggoh NR: -Completion by Q1 (endorsement, ISBN & publication) 2. Loagan Bunut NP, Gunung Gading NP & Piasau NR: -Establish Study Team & ToR -Data collection | A. CADASTRAL SURVEY 1. Commencement of cadastral survey for Loagan Bunut NP 2. Completion of Sabal NP cadastral survey B. MANAGEMENT PLANS 1. Loagan Bunut NP, Gunung Gading NP & Piasau NR: -Data Collection -MP Strategic Planning Workshop | A. CADASTRAL SURVEY 1. 50% completion of Loagan Bunut NP cadastral survey 2. Submission of Sabal NP survey job B. MANAGEMENT PLANS 1. Loagan Bunut NP, Gunung Gading NP & Piasau NR: -MP Draft 1 (Internal Peer-review) -MP Draft 2 (External Peer-review) | A. CADASTRAL SURVEY 1. Completion of Loagan Bunut NP cadastral survey B. MANAGEMENT PLANS 1. Loagan Bunut NP, Gunung Gading NP & Piasau NR: -MP Final Draft -Approved by Controller -Published
7 | Development and upgrading of integrated facilities of 20 Totally Protected Areas 1. Development of staff quarters and utilities at Loagan Bunut National Park 2. Development of Ranger Station at RAMSAR SITE Kuching Wetland National Park 3. Development of facilities and utilities at Maludam National Park | Outcome 2, Outcome 5 | Poject milestone & deliverables achieved | 1. Dialogue session with local community: Maludam NP 2. Recall for Tender: Loagan Bunut NP 3. Call for Tender: Batang Ai NP / Niah NP | Call for Tender: 1. Maludam NP 2. KWNP | Call for Tender: 1. Matang Wildlife Centre 2. Gunung Apeng NP | Call for Tender: 1. Kubah NP
8 | Sarawak Delta Geopark (SDGp) | Outcome 2, Outcome 5 | Project action steps and planned output achieved | i. Appointment of Consultant to develop application dossier (FDS) ii. Submission of Inception Report of application dossier (FDS) iii. Submission of final draft of SDGp Management and Development Plan (EPU) iv. Development of Sarawak Delta Website (FDS) v. Revisit Geosite (JMG) | i. Submission of Letter of Intent (FDS) ii. Scientific Research Data Collection Workshop for aSDUGGp (JMG) iii. Submission of progress report of application dossier (FDS) iv. aSDUGGp Roadshow (Tourism Malaysia/FDS/MTCP) | i. Sarawak Delta International Symposium ii. Sarawak Delta Annual Event iii. Submission of Final Report (Application Dossier) | i. Submission of Application Dossier to Suruhanjaya Kebangsaan UNESCO Malaysia (SKUM) - FDS ii. Inter-Agency Workshop - FDS iii. Readiness assessment by JK Pelaksana Geopark Kebangsaan (MUDeNR/JHS)
9 | Niah NP as UNESCO World Heritage Site (WHS) | Outcome 2, Outcome 5 | Project action steps and planned output achieved | 1. Broadcasting of Niah documentary video. 2. Integrated Management Plan and compilation of feedback for ICOMOS | Set of promotional materials (brochures etc.) for Niah visibility | Kick start of the steering and technical committee roles and functions | Draft of Niah for UNESCO book
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need yearly targets for these outcomes
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on AIP Level 2, there are actions that can contribute to the outcome/output i.e formulation of bamboo policy, develop tissue culture lab, identify site/planters, establish community bamboo farming, etc. Those action should also be included in the initiative milestone and target .
Note on E15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Target should be prepare SDEC paper, get approval for siting (if no approval yet)
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What is the initiative milestone for 2024. In AIP Level 2, we list out several action and output.
Note on E16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: At this stage FDS should be able to indicate where is the area. Must identify and restore identified area (each quarters)

## Quarterly Dashboard Worksheet
No. | INITIATIVE MILESTONES | Impacting which outcome | Measure | Q1 2024 Target | Q1 Achievements | Q2 2024 Target | Q2 Achievements | Q3 2024 Target | Q3 Achievements | Q4 2024 Target | Q4 Achievements
1 | Bamboo Industry Development - To develop nurseries to produce 4,000,000 bamboo seedling by 2030 - To establish 10,000 ha of bamboo plantation by 2030 | Outcome 1 | Poject milestone & deliverables achieved | To produce 162,500 seedlings To plant 375 ha of bamboo | 15, 415 seedlings produced 3.6 ha area planted | To produce 325,000 seedlings To plant 750 ha of bamboo | 4,076 seedlings produced 177.89 ha area planted | To produce 487,500 seedlings To plant 1,125 ha of bamboo | 34,511 seedlings produced cumulative 248.11 ha area planted cumulative | To produce 650,000 seedlings To plant 1,500 ha of bamboo | 45,856 seedlings produced cumulative 262.11 ha area planted cumulative 1 engagement with ANFA Renewables on Oct 8, 2024 and Dec 19, 2024
2 | Furniture Park - Kuching - Tanjong Manis | Outcome 1 | Poject milestone & deliverables achieved | 1. Siting Approval 2. Submission of SDEC Paper | 1. Site approved by 18th March 2024. 2. Submitted 14th January 2024. | Approval of SDEC Paper/ Budget Acquisition | Pending fund allocation from state government | Appointment of consultant, design, survey and soil investigation | STIDC disbursed RM 74,000.00 on 28th June 2024 to Land and Survey for the purpose of topography and perimeter survey in Demak Laut Furniture Park. No consultant appointment is required 1 Investment promotion activity conducted. Participated in Saudi Wood Expo 2024 in 2 to 4 September 2024 | Completion of design, survey and soil investigation. | 1. Pending updates from land and survey on survey status of the lot
3 | Proposed Implementation of Forest Landscape Restoration Throughout Sarawak | Outcome 2, Outcome 1 Outcome 4 | Project action steps and planned output achieved | 1. Site evaluation at 8 identified FLR planting area (Sabal FR, Sempadi FR, Silantek PF, Loba Pulau PF, Kanowit East FR, Similajau FR,Labang FR, Kayangeran FR) 2. Cumulative of 500,000 trees planted and recorded 3.Planting program in conjunction with IDF 2024 | 1. FLR planting area in 8 Permanent Forest Estates (PFE) has been evaluated for planting; 2. 448,151 trees has been recorded as of 31 Mac 2024; 3. Planting program in conjunction with IDF 2024 has been conducted on 21 Mac 2024 at Sabal Forest Reserve with total of 3,000 engkabang jantong (Shorea macrophylla) was planted. | 1. Cumulative of 2 millon trees planted and recorded 2. 5 planting program/collaborations organized 3. Planting program in conjunction with IDF 2024 4. 1 SPA established | 1. Cumulative 2,523,412 has been recorded in Penghijauan Malaysia and has achieved 35 million trees planted on 8 June 2024. 2. Total of 33 programs/collaborations conducted. 3. Premier of Sarawak plant tree number 35,000,000 at Sabal FR in conjunction with State Level IDF 2024. 4. 1 SPA of fast growing species established in Kubah, Matang. | 1. 2 Seed Production Area established 2. 1 FLR Conference conducted in collaboration with ITTO 3. 35 million trees Sarawak's target under 100 Million Trees Planting Campaign achieved. 4. 5 planting program/collaborations organized 5. 1 related MOU signed | 1. 2 Seed Production Area Established i. Pueh Forest Reserve @ 51 mother trees ii.Sabal Forest Reserve @ 90 mother trees (geronggang) 2. Asia-Pacific Regional Conference on Forest Landscape Restoration 2024 in collaboration with ITTO was held in Kuching, Sarawak on 27 - 28 August 2024. 3. Achieved 35 million tree planting target on 8 June 2024. Premier of Sarawak has planted tree number 35 million at Sabal FR in conjunction with the Satet-Level IDF 2024. 4. 21 planting program/collaborations organized in Q3 5. MoU signed between FDS and Bintulu Port Holding Berhad on 8 June 2024 for restoration and Greening Sarawak Campaign activities. | 1. Cumulative 7 million trees planted (20,000ha area) in 2024 2. 5 planting program/collaborations 3. Cumulative of 120 jobs created through community engagement in 2024 4. 100% planting data updated in Penghijauan Malaysia
4 | Conservation and Protection of Wetlands and Watershed Within Heart of Borneo Sarawak (HoB) | Outcome 2, Outcome 5 | Project action steps and planned output achieved | 1. Workshop of assessent Wetland area for Ramsar Site 2. Multi-disciplinary assessment and feasibility study of Kuala Rajang 3. Engagement with communities in Wetland area, Sarikei 4. Preparation for appoitment of consultant (Multi-disciplinary assessment and feasibility study of Kuala Rajang) | 1. Workshop of assessment Wetlands area as Ramsar site was conducted on 20 - 21 Februari 2024 in Kingwood Hotel, Sibu. 2. Multi-disiplinary asessment and feasibility study of Kuala Rajang was conducted in 25 - 27 Mac 2024 in Kuala Selalang, Sarikei. 3. Engagement program with communities in Wetland area were conducted in 19 March 2024 in Palong, Tanjung Manis and 23 March 2024 in Kuala Selalang, Sarikei. 4. Preparation for appointment of consultant was prepared (. | 1. Communities Development Program in Watershed area, Baleh 2. Organize Program of Communication, Education & Public Awareness (CEPA) in Wetland area, Sarikei | 1. Discussion on organizing Communication Development Program with communities in Watershed area on 16 Mei 2024. Program been postponed to August 2024. 2. Communication, Education and Public Awareness (CEPA) Program being conducted with wetland communities on 12 June 2024. | 1. Appoitment of consultant to conduct Multi-disciplinary assessment and feasibility study of Kuala Rajang (Biodiversity study) 2. Program of Communication, Education & Public Awareness (CEPA) in Watershed area, Baleh 3. Communities Development Program in Wetland area, Sarikei | 1. Appointment of consultant to conduct Multi-disciplinary assessment and feasibility study of Kuala Rajang in process of preparing document (Berdasarkan maklumbalas daripada pihak MUDeNR berkenaan permohonan kelulusan pencalonan kawasan Kuala Rajang sebagai Tapak Ramsar yang baru di Sarawak bernombor rujukan: 2/MUDeNR/900-1/1/8 bertarikh 13.11.2024, pihak Jabatan masih dalam proses perbincangan dan seterusnya membawa perkara tersebut kepada pihak SFC berkenaan kawasan yang di bawah bidang kuasa pihak SFC. Oleh itu, proses lantikan perunding dijangka akan selesai pada Q2/2025.) 2. Community Development Program (study tours to Ramsar site - Kuching Wetland National Park) was conducted in 10 - 12 September 2024 3. Karnival Pembangunan Komuniti Perhutanan Tahun 2024 bersama komuniti Tadahan Air, Baleh pada 14 - 22 September 2024 4. Program Communication, Education & Public Awarenesss in Watershed Area (Program Penghasilan Kraftangan Tempatan bersama Komuniti Kawasan Tadahan Air, Baleh, Kapit pada 24 - 26 September 2024). | 1. Workshop to prepare Proposal of Ramsar site 2. Annual Workshop of Wetland and Watershed involving stakeholders and communities
5 | Strengthening Forest Enforcement Through Advancing the Technology and Equipments | Outcome 3 | Project action steps and planned output achieved | 1.Prepare & process tender document (rental of land & river transportation for forest enforcement activities at Kapit, Sibu, Sarikei, Bintulu, Miri & Limbang Region) 2. Appointment of tenderer for tender (rental of land & river transportation for forest enforcement activities at Kapit, Sibu, Sarikei, Bintulu, Miri & Limbang Region) 3. Implementation of forest enforcement activities 4. Workshop on Awareness Programme (Forest Enforcement) 5. Awareness Program (Forest Enforcement) – 1 programme 6. Prepare document on Forest Training (Technical training for forest enforcement officers) 7. Technical training for forest enforcement officers – 1 program | 1. Mesyuarat Jawatankuasa Cadangan Teknikal dan Kewangan di peringkat Jabatan Hutan Sarawak dan Mesyuarat Rundingan Harga untuk dokumen Tender (rental of land & river transportation for forest enforcement activities at Kapit, Sibu, Sarikei, Bintulu, Miri & Limbang Region) 2. Workshop on Awareness Programme (Forest Enforcement) at Primier Hotel, Sibu on 07 -08 Februari 2O24. 3. Training on forest enforcement (Seminar Jelajah Kesedaran dan Penguatkuasaan Hutan 2024) at Kuching, Sibu, Bintulu and Miri | 1. Implementation of forest enforcement activities – 3 Operasi Rengas Bersepadu (combating Illegal logging) 2. Awareness Program (Forest Enforcement) – 3 programmes 3. Technical training for forest enforcement officers – 2 programmes | 1.Award tender on land transport (4WD) and river (boat) to tenderer – 6 tender documents (Sarikei, Sibu, Kapit, Bintulu, Miri and Limbang Region) 2.Forest enforcement Integrated Operations – 3 operation (Limbang, Miri and Sibu Region) Rental of land transport (4WD) during forest enforcement opration 3.Forest Enforcement awareness programme – 3 programmes 4.Forest enforcement technical training – 2 programmes | 1. Implementation of forest enforcement activities – 4 Operasi Rengas Bersepadu (combating Illegal logging) 2. Awareness Program (Forest Enforcement) – 3 programmes 3. Technical training for forest enforcement officers – 1 programmes | 1. 4 series of Operasi Rengas Bersepadu (combating Illegal logging) conducted in Kuching/Sri Aman, Kapit, Bintulu and Miri Region 2. 2 Awareness Program on Forest Enforcement conducted at Long Busang Kapit, Long lama Miri 3. Latihan Pengukuhan Penguatkuasaan Hutan (Technical training for forest enforcement officers) conducted at Centreal Region (Sibu/Kapit/Sarikei) and Northern Region (Bintulu/Miri/Limbang) | 1. Implementation of forest enforcement activities – 2 Operasi Rengas Bersepadu (combating Illegal logging) 2. Awareness Program (Forest Enforcement) – 2 programmes 3. Technical training for forest enforcement officers – 1 programmes
6 | Management and strengthening protection for selected Totally Protected Areas 1. Securing TPA Integrity through cadastral perimeter survey of boundaries (27 NPs) 2. TPA Management Plans developed (4 NPs) Note: Under Tourism Sector No. 6.13a: TPA-Mgt Plans integrated with Tourism MP renewed (12 NPs) No. 6.13b: New TPA Mgt Plans with Tourism MP incorporated (11 NPs) | Outcome 2, Outcome 5 | Poject milestone & deliverables achieved | A. CADASTRAL SURVEY 1. Appointment of consultant for Loagan Bunut NP Cadastral survey >Delayed 2. 50% Completion of Sabal NP cadastral survey >Target Achieved B. MANAGEMENT PLANS 1. Limbang Mangrove NP/ Kuching Wetland NP/ Wind Cave NR/ Fairy Cave NR/ Semenggoh NR: -Completion by Q1 (endorsement, ISBN & publication) > Delayed 2. Loagan Bunut NP, Gunung Gading NP & Piasau NR: -Establish Study Team & ToR /Data collection >Target Achieved | A. CADASTRAL SURVEY 1. Loagan Bunut NP Targeted consultant appointment by Q1 2024 delayed to Q2, 2024. SDEC paper submitted to MUDeNR on 18.04.2024 to seek additional project ceiling (RM826K) to accommodate the increase in cost for the appointment of surveyor. 2. Sabal NP Overall survey progress is at 71%. Targeted completion by Q2 2024. B. MANAGEMENT PLANS 1. Limbang Mangrove NP/ Kuching Wetland NP/ Wind Cave NR/ Fairy Cave NR/ Semenggoh NR: Completion delayed to Q2 2024. LMNP & KWNP: Draft write up completed. Reviewing process in progress. Targeted completion date affected by the delay of the Conservation Strategy Planning Workshop which required an external facilitator. Write up process also delayed due to limited data availability, resulting in more desktop research needed, especially on RAMSAR site management planning. Targeted completion by Q2 2024. WCNR: Draft write-up completed and still in reviewing process. Targeted completion date is affected by the need to revise the “implementation plan” due to limited data availability on certain points. Targeted completion by Q2 2024. FCNR: Final amendments is in progress. Delay due to the need to revise the plan based on feedback from both internal and external peer reviewers, as well as the process of applying for an ISBN serial number. Targeted completion: Q2 2024 SNR: Final amendments is in progress. Targeted completion date affected due to delay in the amendment process and requirement for ISBN Serial Number application. The process period has been extended as per proof reader’s request (external reviewer) and application for ISBN Serial Number only can be made once manuscript page number finalized and endorsed. Targeted completion by Q2 2024. 2. Loagan Bunut NP, Gunung Gading NP & Piasau NR: 26.02.24: Study Team has been established. 21.03.24: ToR for Development of Management Plan and proposal to conduct Conservation Strategy Planning Workshop approved by Controller. In the pipeline for Q2 2024: Ecotourism product assessment, meeting with local communities and Conservation Strategy Planning Workshops. | A. CADASTRAL SURVEY 1. Commencement of cadastral survey for Loagan Bunut NP 2. Completion of Sabal NP cadastral survey B. MANAGEMENT PLANS 1. Loagan Bunut NP, Gunung Gading NP & Piasau NR: -Data Collection -MP Strategic Planning Workshop | 1. Loagan Bunut NP: 18.04.2024: SDEC paper submitted for additional ceiling for consultant appointment. SFC has informed the Ministry/EPU at Sesi Libat Urus Kajian Keperluan Sililng Peruntukan Projek Pembangunan (31.05.2024) on this request to cover the increase in cost for appointing surveyor (RM2.29Mil is required to be committed for the consultant appointment). Targeted consultant appointment has been delayed to Q3, 2024. 2. Sabal NP: Cadastral survey is at 74% completed as at Q2 2024. On 24.06.2024, Consultant applied for EOT for field work for 8 weeks from 1st July until 30th August 2024. On the ground inspection at Sabal NP was carried out on 28.06.2024 before EOT endorsement. Pending field report. Completion delayed to Q3, 2024. 1. Limbang Mangrove NP/ Kuching Wetland NP/ Wind Cave NR/ Fairy Cave NR/ Semenggoh NR: Completion delayed to Q3 2024. LMNP (90% completion): Draft write up completed. Reviewing process in progress. Reviewing EAAFP MOP10/D1: Pelan Strategik Perkongsian East Asian-Australasian Flyway 2019-2028 to streamline the plan with LMNP MP. KWNP (80% competion): Draft write up completed. Reviewing, updating and incorporating KWNP MP 2011-2020 in progress. WCNR (90% completion): Draft write-up completed and still in reviewing process. Need to revise the “implementation plan” due to limited data availability on certain points. FCNR (99% completion): 24.05.2024: FCNR MP endorsed by Controller and finalized for publication. 05.06.2024: ISBC obtained. 08.07.2024: Printing of management plan in progress. SNR (99% completed): 29.04.2024: SNR MP endorsed by Controller and finalized for publication. 05.06.2024: ISBC No. obtained. 08.07.24: Printing in progress. 2. Loagan Bunut NP, Gunung Gading NP & Piasau NR: > Data collection and compilation stage. > 04.07.24: Conservation Strategy Planning Workshop Proposal approved by JPT and to be conducted in Q3 2024. | A. CADASTRAL SURVEY 1. 50% completion of Loagan Bunut NP cadastral survey 2. Submission of Sabal NP survey job B. MANAGEMENT PLANS 1. Loagan Bunut NP, Gunung Gading NP & Piasau NR: -MP Draft 1 (Internal Peer-review) -MP Draft 2 (External Peer-review) | Securing TPA integrity through cadastral perimeter survey of boundaries (14 locations)Securing TPA integrity through cadastral perimeter survey of boundaries (13 locations) 6. Loagan Bunut NP – 59% completion Data collection and compilation stage. In the pipeline: > Loagan Bunut NP Threat Ranking & Prioritization Workshop: 21-25.10.24 > 1st Sarawak Zoning Training Workshop; Approach, Tools, Categories and Guidelines: 15-16.10.24 > 2nd Sarawak Training Workshop; Develop your Zoning Maps – Case Study GGNP, LBNP & PNR: 12-13.11.24 7. Gunung Gading NP (46% completion) Data collection and compilation stage. In the pipeline: >Gunung Gading NP Threat Ranking & Prioritization Workshop: 21-25.10.24 >1st Sarawak Zoning Training Workshop; Approach, Tools, Categories and Guidelines: 15-16.10.24 >2nd Sarawak Training Workshop; Develop your Zoning Maps – Case Study GGNP, LBNP & PNR: 12-13.11.24 [Completed: 19.6% ] 1. Sabal NP: 95.5% completed Consultant applied for EOT for field work for 8 weeks from 1st July until 30th August 2024. Consultant finalizing the data before submission to Land & Survey. 2. Loagan Bunut NP: SDEC paper submitted on 18.04.2024 to seek additional project ceiling (RM826K) due to increase in cost for appointment of surveyor. SFS in principle approved the additional ceiling on 15.08.2024 during budget examination. Pending receipt of official approval in order to proceed with consultant appointment. Prepare Management plans for 4 TPAs [Completed: 72.5% ] [6.13a: TPA-Mgt Plans integrated with Tourism MP renewed (12 NPs) /48.5% New TPA Mgt Plans with Tourism MP incorporated (11 NPs)] [Completed: 21% ] Limbang Mangroves NP: 90% completion Draft write up completed. Reviewing process in progress. Delayed due to limited data availability, resulting in more desktop research needed. Reviewing EAAFP MOP10/D1: Pelan Strategik Perkongsian East Asian-Australasian Flyway 2019-2028 to streamline the plan with LMNP MP. Proposed area for EAAFP. 2. Kuching Wetland NP: 80% completion Reviewing, updating & incorporating KWNP MP 2011-2020 in progress. Delay due to limited data availability, resulting in more desktop research needed, especially on RAMSAR site management planning. 3. Wind Cave NR: 90% completion Draft write-up completed and still in reviewing process. Revising “implementation plan” due to limited data availability. 6. Loagan Bunut NP – 59% completion Data collection and compilation stage. In the pipeline: > Loagan Bunut NP Threat Ranking & Prioritization Workshop: 21-25.10.24 > 1st Sarawak Zoning Training Workshop; Approach, Tools, Categories and Guidelines: 15-16.10.24 > 2nd Sarawak Training Workshop; Develop your Zoning Maps – Case Study GGNP, LBNP & PNR: 12-13.11.24 7. Gunung Gading NP (46% completion) Data collection and compilation stage. In the pipeline: >Gunung Gading NP Threat Ranking & Prioritization Workshop: 21-25.10.24 >1st Sarawak Zoning Training Workshop; Approach, Tools, Categories and Guidelines: 15-16.10.24 >2nd Sarawak Training Workshop; Develop your Zoning Maps – Case Study GGNP, LBNP & PNR: 12-13.11.24 8. Piasau NR: (46% completion) Data collection and compilation stage. In the pipeline: > Piasau NR Threat Ranking & Prioritization Workshop: 21-25.10.24 >1st Sarawak Zoning Training Workshop; Approach, Tools, Categories and Guidelines: 15-16.10.24 >2nd Sarawak Training Workshop; Develop your Zoning Maps – Case Study GGNP, LBNP & PNR: 12-13.11.24 | A. CADASTRAL SURVEY 1. Completion of Loagan Bunut NP cadastral survey B. MANAGEMENT PLANS 1. Loagan Bunut NP, Gunung Gading NP & Piasau NR: -MP Final Draft -Approved by Controller -Published
7 | Development and upgrading of integrated facilities of 20 Totally Protected Areas 1. Development of staff quarters and utilities at Loagan Bunut National Park 2. Development of Ranger Station at RAMSAR SITE Kuching Wetland National Park 3. Development of facilities and utilities at Maludam National Park | Outcome 2, Outcome 5 | Poject milestone & deliverables achieved | 1. Dialogue session with local community: Maludam NP - Target achieved 2. Recall for Tender: Loagan Bunut NP - Target achieved 3. Call for Tender: Batang Ai NP / Niah NP - Target achieved | Maludam NP: SPA provisional approval received in letter dated on 18.03.2024. Dialogue session with the local community of Rumah Panjang Tg. Baru done on 28.03.2024. Currently, under detail design development stage. Loagan Bunut NP: Re-Tender had been called on 24.04.2024 and shall be closed on 20.05.2024. BANP: Tender had been called on 02.02.2024 and closed on 29.2.2024. Currently under Tender evaluation stage. Niah NP: Tender had been called on 11.03.2024 and closed on 09.04.2024. Currently under Tender evaluation stage. | Call for Tender: 1. Maludam NP 2. KWNP | 1. Maludam NP (Utilities connection & walkway): Dialogue session with the local community of Rumah Panjang Tg. Baru done on 28.03.2024. MoM of the dialogue session was confirmed signed and returned on 6.6.2024. Letter issued on 2.7.2024 to L&S Betong to request for joint inspection for identification of affected crop yields. Call for tender delayed. 2. KWNP (Ranger station and temporary access):Tender had been called on 20.05.2024 and closed on 18.06.2024. Currently under Tender evaluation stage. Call for tender completed. 3. Kubah NP (Staff accommodation & visitors facilities): Detailed Site Survey & Investigation to be done by appointed consultant. Site plan, schematic design and CTK to be presented on 13.8.2024. 5. Matang Wildlife Centre (Staff accommodation & facilities):Tender documentation ready on 26.6.2024. Plan Tender stage and award in Q3 2024. 6. Batang Ai NP (Solar hybrid): Re-Tender done on 13.6.2024 and closed on 9.7.2024. Currently under Tender evaluation stage. Call for re-tender completed. 7. Loagan Bunut NP (Staff quarters & utilities): Re-Tender was called on 24.4.2024 and closed on 20.5.2024. Currently still under Tender evaluation stage. Call for re-tender completed. 8. Gunung Apeng NP (Ranger station): Pending reply on land acquisition enquiry to Land & Survey. Proposal to be refined to suit and consideration of optional site upon finalization of boundary demarcation exercise for scope of work submission under 13MP. 9. Bukit Lima NR (Boardwalk & One Stop Centre at North Gate): Called for Tender on 22.04.2024 and closed on 14.05.2024. SPA application resubmission done on 26.04.2024 upon approval of plan in technical committee meeting on 03.04.2024. Currently, under Tender evaluation stage. Call for tender completed. | Call for Tender: 1. Matang Wildlife Centre 2. Gunung Apeng NP | To develop and upgrade facilities at selected manned and unmanned TPAs [Completed: 28%) Maludam NP (Utilities connection & walkway): Management Tender Committee decided to award the tender to the successful tenderer during the meeting on 24 September 2024. Plan Tender stage and award in Q4 2024. 2. KWNP (Ranger station and temporary access): Board Tender Committee decision to award to successful Contractor as per memo issued on 25.09.2024. Plan kick-off meeting soon after LOA issued in October 2024. 3. Kubah NP (Staff accommodation & visitors facilities): 17.9.2024: Conceptual plan approved. Detail design in progress for plan Tender in Q4. 4. Matang Wildlife Centre (Staff accommodation & facilities): Management Tender Committee decided to award the tender to the successful tenderer during the meeting on 24 September 2024. Plan Tender stage and award in Q4 2024. | Call for Tender: 1. Kubah NP
8 | Sarawak Delta Geopark (SDGp) | Outcome 2, Outcome 5 | Project action steps and planned output achieved | i. Appointment of Consultant to develop application dossier (FDS) ii. Submission of Inception Report of application dossier (FDS) iii. Submission of final draft of SDGp Management and Development Plan (EPU) iv. Development of Sarawak Delta Website (FDS) v. Revisit Geosite (JMG) | i)Consutant for development of Dossier has been appointed by 19 March 2024 ii)Development of SDGp Website : waiting for WOT approval from SFS iii) Submission Interim Report 2 SDGp Management and Development Plan (EPU) by 25 March 2024 iv)Revisit Geosite for monitoring the current status on 18-22 March 2024 | i. Submission of Letter of Intent (FDS) ii. Scientific Research Data Collection Workshop for aSDUGGp (JMG) iii. Submission of progress report of application dossier (FDS) iv. aSDUGGp Roadshow (Tourism Malaysia/FDS/MTCP) | i. Letter of Intent submitted to UNESCO Secretariat on 31 May 2024 and acknowledged by the secretariat on 10 June 2024 ii. Scientific Research Data Collection Workshop for aSDUGGp held on 23-25 April 2024 iii. Inception report submitted on 14 May 2024 First progress report submitted on 31 May 2024 iv. aSDUGGp Roadshow (Media Fam Trip Berambeh ke Sarawak Delta Geopark) on 4-9 June 2024 | i. Sarawak Delta International Symposium ii. Sarawak Delta Annual Event iii. Submission of Final Report (Application Dossier) | i. Seminar on Sarawak Delta Geopark Expedition held on 17-18 July 2024 ii. Final Draft Report (Application Dossier) submitted on 30 September 2024 | i. Submission of Application Dossier to Suruhanjaya Kebangsaan UNESCO Malaysia (SKUM) - FDS ii. Inter-Agency Workshop - FDS iii. Readiness assessment by JK Pelaksana Geopark Kebangsaan (MUDeNR/JHS)
9 | Niah NP as UNESCO World Heritage Site (WHS) | Outcome 2, Outcome 5 | Project action steps and planned output achieved | 1. Broadcasting of Niah documentary video. 2. Integrated Management Plan and compilation of feedback for ICOMOS | 1. All four episodes have been aired on TVS throughout 31 January until 28 February (weekly). Rights for TVS to air is for 3 years at their discretion. 2. Formulation of Integrated Conservation Management Plan was approved by State Planning Authority on 8 February 2024 and submitted to ICOMOS on 28 February 2024. | Set of promotional materials (brochures etc.) for Niah visibility | Publication of Articles: On 27.05.2024 JPP approved the technical and financial proposal of the consultant. Received approval from the SFS office to proceed (12 July 2024) . Award letter to be sent to the consultant soon. Note: The Archaeological Heritage of Niah National Park’s Caves Complex has been inscribed as a UNESCO WHS on 28.07.2024. | Kick start of the steering and technical committee roles and functions | Archaeological Heritage of Niah National Park’s Caves Complex has been inscribed as a UNESCO WHS on 28.07.2024. Post inscription activities: 1. Technical committee for the utilization of the federal fund was formed on 27 July 2024. 2. Request for the Steering Committee meeting had been sent out on 27 Sept 2024 and now pending for confirmation. | Draft of Niah for UNESCO book
10 | Quantifying Forest Carbon Stock In Sarawak | Outcome 1, Outcome 3, Outcome 5 | Project action steps and planned output achieved | 1. Purchase CN Analyzer System via tender (advertised on 6/2/24) 2. Workshop on belowground carbon cycling in forest ecosystem. 3. Prepare tender document for renting of transport. 4. Purchase field survey equipment. 5. Maintenance of laboratory equipment. 6. Prepare MOU document with Kyushu University. 7. Prepare document for appointment of consultant for forest biomass assessment. 8. Planning to purchase tablet (ICT). | 1. Request to purchasing tablet had been submitted. PO/SO for some equipment and consumables have been issued on 25/3. 2. First field sampling conducted at Lambir, Miri from 30/3-5/4. 3. SO for weighing scale and fumehood maintenance has been issued on 25/3. 4. In the process of writing letter to EPU for appointing consultant. 5. Below ground carbon cycling in forest ecosystem training was attended by two officers from 29 Feb to 9 Mar 2024 in Japan. | 1. Forest biomass assessment at various forest in Sarawak. 2. Attend workshop on carbon trading. 3. Appointment of consultant for biomass assessment. 4.Attend Tropical Forest Carbon Inventory Short Course by FRIM. | 1. Assessment conducted at Lambir Hills and Samunsam 2. Carbon trading workshop was successfully attended at Netherland end of Apr. 3. SFS just approved on 10/7 to invite UPM as one of the vendor for biomass assessment work. 4. Tropical Forest Carbon Inventory Short Course was attended by two officers (PMD and RDD each) | 1. Signing of MOU with Kyushu University, Japan. 2. Forest biomass assessment at various forest in Sarawak. | 1. Training and MOU signing ceremony successully held at Fukuoka, Japan on 23-27 July 2024 2. Received CN analyser instrument on 4/9/2024. Currently installing the gas piping and setting up facilities. 3. Conducted one workshop on "Karbon Hutan bagi Pemilik Tanah Hak Adat Bumiputera at Sibu on 20-22 August 2024. 4. Currently pending a letter to EPU on consulation work and also company profile from UPM serdang. 5. Assessment of biomass was conducted in Aug at mangrove plot at Samunsam. 6. Sebut harga for transport was completed and awarded in Sept 2024 | 1. Organize seminar for knowledge sharing. 2. Prelimary report on biomass findings. 3. Forest biomass assessment at various forest in Sarawak.
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Target should be prepare SDEC paper, get approval for siting (if no approval yet)

## FMC
No. | Forest Timber Licence | FMU | Timber Group | Area (ha) | No. | FPMU | Area (Ha)
1 | T/4317 | Anap Muput FMU | Shin Yang | 83535 | 1 | Segan FPMU (LPF 0014) - Samling Timber Sdn. Bhd. | 10332
2 | T/0294 | Ravenscourt FMU | Samling | 117941 | 2 | Penyuan FPMU (LPF 0018) - Shin Yang Forestry Sdn. Bhd. | 15261
3 | T/3491 | Kapit FMU | Ta Ann | 149877 | 3 | Lana FPMU (LPF 0006) - Samling Restoration ( Bintulu) Sdn. Bhd. | 9393
4 | T/3228 | Linau FMU | Shin Yang | 72710 | 4 | Marudi FPMU (LPF 0008) - Samling Reforestation (Bintulu) Sdn. Bhd. | 19941
5 | T/0280 & T/9115 | Ulu Trusan FMU | Samling | 92279 | 5 | Masama FPMU (LPF 0019) - Shin Yang Forestry Sdn. Bhd. | 11946
6 | T/0560 | Raplex FMU | Ta Ann | 63993 | 6 | Kejin Long Lama FPMU (LPF 0017) - Shin Yang Forestry Sdn. Bhd. | 28093
7 | T/3343 | Melatai Para FMU | STIDC | 49524 | 7 | Kuala Baram FPMU (LPF 0004) - Samling Timber Sdn. Bhd. | 3000
8 | T/3135 | Pasin FMU | Ta Ann | 132151 | 8 | Paong FPMU (LPF 0021) - Samling Reforestation (Bintulu) Sdn Bhd. | 24834
9 | T/0413 | Gerenai FMU | Samling | 148305 |  |  | 122800
10 | T/3400 | Gaat Mengiong FMU | STIDC | 66190
11 | T/3476 | Entulu Melatai FMU | WTK | 55112
12 | T/3342 | Danum FMU | Shin Yang | 200383
13 | T/3361 | Mujong Melinau FMU | Subur Tiasa | 41303
14 | T/3291 | Segaham FMU | KTS | 38984
15 | T/3290 | Taman FMU | KTS | 34317
16 | T/0341 | Patah Tutoh FMU | KTS | 38687
17 | T/3432 | Nibong FMU | STIDC | 54143
18 | T/3401 | Mengiong Gaat FMU | STIDC | 36091
19 | T/3669 | Oya Balingian FMU | STIDC | 78051
20 | T/3371 | Baleh Balui FMU | RH | 215088
21 | T/3370 | Penuan Lebuwai FMU | RH | 132416
22 | T/3670 | Bah Sama FMU | Samling | 35379
23 | T/3372 | Mengiong Entulu FMU | Shin Yang | 64974
24 | T/0405 | Layun FMU | Samling | 142790
25 | T/0390 | Tama Abu FMU | Samling | 182998
Total Area |  |  |  | 2327221

## Timber Export Value
TIMBER EXPORT VALUE (RM)
Month | 2022 | 2023 | 2024 | 2025
JAN | 408531176.77 | 263569916.63 | 276004972.69
FEB | 239761718.38 | 226356164.3 | 191530929.47
MAR | 394935606.46 | 261778295.29 | 214907671.7
APR | 400891037.27 | 215771835.07 | 232014272.14
MAY | 345725679.36 | 324280067.64 | 324627750.87
JUN | 268966198.26 | 235560482.89 | 212303812.34
JUL | 359792973.34 | 244689028.37 | 274788036.68
AUG | 310830376.16 | 344761866.36 | 210420404.31
SEP | 318990291.52 | 210214202.2 | 191837139
OCT | 304693148.3 | 266639022.25
NOV | 303936172.09 | 296062485.55
DEC | 289911760.38 | 251155864.77
| 3946966138.29 | 3140839231.32 | 2128434989.2

## Data - Chart (Deg. Area)
Month | Total Degraded Area Restored (Ha) Year 2022 | Total Degraded Area Restored (Ha) Year 2023 | Total Degraded Area Restored (Ha) Year 2024
Jan | 787.01 | 1856.37 | 3146.6
Feb | 912.41 | 3449.94 | 6660.5
Mar | 513.04 | 2284.69 | 3203.8
Apr | 428.18 | 1807.69 | 1871.5
May | 485.08 | 3255.8 | 2750.2
Jun | 1277.9 | 3120.66 | 3396.3
Jul | 745.15 | 2562.38
Aug | 762.69 | 2474.93
Sep | 579.09 | 3251.93
Oct | 676.27 | 3086.64
Nov | 2012.35 | 3081.63
Dec | 1114.64 | 3240.14
| 10293.81 | 33472.8 | 21028.9
Half Yearly Report

## (Detail)Timber Export Value
LAMPIRAN I
A. EXPORT VOLUME & VALUE OF LOG AND TIMBER PRODUCTS (JANUARY - DECEMBER 2024)
1. Volume (Isipadu)
Product (Produk) | Unit Isipadu | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total (Jumlah) | Monthly Average (Purata bulanan) | Unjuran 2024 | Sebenar 2023 | Perubahan (%)
LOG (Natural Forest) | m3 | Jan: 67316.6555; Feb: 25843.3032; Mar: 33506.9341; Apr: 55420.5252; May: 36887; Jun: 28280.19 | 247254.608 | 61813.652 | 741763.824 | 558997.6091 | 32.6953
LOG (Planted Forest) |  | Jan: 0; Feb: 0; Mar: 0; Apr: 0 | 0 | 0 | 0 | 0 | 0
PLYWOOD |  | Jan: 50091.2753; Feb: 33453.7755; Mar: 44799.4178; Apr: 48027.0078; May: 83767.65; Jun: 56307.37 | 316446.4964 | 79111.6241 | 949339.4892 | 613548.2243 | 54.7294
SAWNTIMBER |  | Jan: 8967.9779; Feb: 3292.1212; Mar: 7773.8731; Apr: 12124.9915; May: 10595; Jun: 9207 | 51960.9637 | 12990.2409 | 155882.8911 | 130326.1516 | 19.6098
FIBREBOARD |  | Jan: 15959.2173; Feb: 14268.5027; Mar: 13819.3517; Apr: 18989.8478; May: 14138.26; Jun: 10344 | 87519.1795 | 21879.7949 | 262557.5385 | 165057.07 | 59.0708
VENEER |  | Jan: 645.5133; Feb: 1171.349; Mar: 731.6274; Apr: 872.3992; May: 1194.26; Jun: 1063 | 5678.1489 | 1419.5372 | 17034.4467 | 16361.2602 | 4.1145
DOORSKIN |  | Jan: 1702.0794; Feb: 710.5024; Mar: 1208.9689; Apr: 2094.1046; May: 1791.58; Jun: 613.91 | 8121.1453 | 2030.2863 | 24363.4359 | 24277.3695 | 0.35451
LAMINATED BOARD/FLOORING |  | Jan: 581.1774; Feb: 591.721; Mar: 479.6736; Apr: 727.6005; May: 569.61; Jun: 914.95 | 3864.7325 | 966.1831 | 11594.1975 | 6160.4499 | 88.2037
PARTICLEBOARD |  | Jan: 907.248; Feb: 821.3051; Mar: 193.6598; Apr: 567.8396; May: 877.07; Jun: 844.2 | 4211.3225 | 1052.8306 | 12633.9675 | 12524.4633 | 0.87432
DOOR PANELS & FRAMES |  | Jan: 2274.8713; Feb: 1569.4555; Mar: 1628.0726; Apr: 1098.2501; May: 1665.41; Jun: 205 | 8441.0595 | 2110.2649 | 25323.1785 | 14998.9675 | 68.8328
MOULDING |  | Jan: 179.3883; Feb: 172.4; Mar: 202.6071; Apr: 153.5116; May: 258.54; Jun: 43.31 | 1009.757 | 252.4392 | 3029.271 | 2286.3284 | 32.495
OTHER PRODUCTS |  | Jan: 1326.7331; Feb: 1604.9424; Mar: 1734.5961; Apr: 1797.7832; May: 1086.74; Jun: 1377.4 | 8928.1948 | 2232.0487 | 26784.5844 | 16692.461 | 60.4592
TOTAL (Jumlah) [m3] |  | 149952.1368 | 83499.378 | 106078.7822 | 141873.8611 | 152831.12 | 109200.33 | 0 | 0 | 0 | 0 | 0 | 0 | 743435.6081 | 185858.902 | 2230306.8243 | 1561230.3547 | 42.8557
% |  | 20.1702 | 11.2316 | 14.2687 | 19.0835 | 20.5574 | 14.6886 | 0 | 0 | 0 | 0 | 0 | 0 | 100
FURNITURE /FURNITURE PARTS (UNT) | Unit | Jan: 182609; Feb: 93361; Mar: 238311; Apr: 92060; May: 247326; Jun: 74410 | 928077 | 232019.25 | 2784231 | 1950808 | 42.7219
WOODEN PALLETS |  | Jan: 0; Feb: 0; Mar: 0; Apr: 0 | 0 | 0 | 0 | 100 | -100
SCENTED WOOD | KGM | Jan: 11.9; Feb: 0; Mar: 0; Apr: 0; May: 110 | 121.9 | 30.475 | 365.7 | 160 | 100
CHARCOAL/BRIQUETTE | Tonne | Jan: 221.9588; Feb: 284.5505; Mar: 213.055; Apr: 207.9185; May: 321.22; Jun: 183.82 | 1432.5229 | 358.1307 | 4297.5685 | 2156.7066 | 99.2653
WOOD PELLETS |  | Jan: 11029; Feb: 20000; Mar: 0; Apr: 0; May: 26640 | 57669 | 14417.25 | 173007 | 57403.914 | 201.3854
WOODCHIP |  | Jan: 28236.919; Feb: 20299.708; Mar: 35407.916; Apr: 0; May: 28084.69; Jun: 18054.47 | 130083.703 | 32520.9258 | 390251.109 | 275188.935 | 41.8121
OTHERS PRODUCTS: Blockboard,Dowels,Finger Jointed,Lamin Board, Laminated Beam/Post,
Laminated Veneer Lumber(LVL), Wooden Stakes.Wooden Handle
2. FOB Value (Nilai FOB) [RM'000]
Product (Produk) |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total (Jumlah) | Monthly Average (Purata bulanan) | Unjuran 2024 | Sebenar 2022 | Perubahan (%)
LOG (Natural Forest) |  | Jan: 53860713.61; Feb: 21537582.15; Mar: 27128845.31; Apr: 45439551.83; May: 29842376.12; Jun: 22868276.53 | 200677345.55 | 50169336.3875 | 602032036.65 | 499193393.05 | 20.601
LOG (Planted Forest) |  | Jan: 0; Feb: 0; Mar: 0; Apr: 0 | 0 | 0 | 0 | 0 | 0
PLYWOOD |  | Jan: 118310876.43; Feb: 82313900.91; Mar: 104429009.65; Apr: 107170847.56; May: 177144719.72; Jun: 120402890 | 709772244.27 | 177443061.0675 | 2129316732.81 | 1496779471.09 | 42.2599
SAWNTIMBER |  | Jan: 14521087.32; Feb: 4305659.58; Mar: 11252874.89; Apr: 18709091.7; May: 20158976.83; Jun: 13945197.97 | 82892888.29 | 20723222.0725 | 248678664.87 | 248420847.32 | 0.10378
FIBREBOARD |  | Jan: 38203209.41; Feb: 33126295.37; Mar: 30032985.41; Apr: 36919940.37; May: 32547354.47; Jun: 24016847.92 | 194846632.95 | 48711658.2375 | 584539898.85 | 398851485.85 | 46.5558
VENEER |  | Jan: 1223457.99; Feb: 1487045.29; Mar: 1153615.45; Apr: 1475275.17; May: 2327428.58; Jun: 1919900.56 | 9586723.04 | 2396680.76 | 28760169.12 | 27907947.2 | 3.0537
DOORSKIN |  | Jan: 4916866.96; Feb: 2093375.17; Mar: 3409425.29; Apr: 5850429.4; May: 4936774.61; Jun: 1703180.29 | 22910051.72 | 5727512.93 | 68730155.16 | 70021139.71 | -1.8437
LAMINATED BOARD/FLOORING |  | Jan: 3631852.61; Feb: 4692498.23; Mar: 3569787.42; Apr: 5075148.47; May: 3926869.42; Jun: 5852695.03 | 26748851.18 | 6687212.795 | 80246553.54 | 33478873.49 | 139.6931
PARTICLEBOARD |  | Jan: 1106008.34; Feb: 1013317.26; Mar: 235308.89; Apr: 685382.59; May: 1104926.05; Jun: 1037181.46 | 5182124.59 | 1295531.1475 | 15546373.77 | 14929472.92 | 4.1321
DOOR PANELS & FRAMES |  | Jan: 4333801.42; Feb: 3013046.64; Mar: 3090492.26; Apr: 2087614.44; May: 3156646.04; Jun: 408406 | 16090006.8 | 4022501.7 | 48270020.4 | 27297828.01 | 76.8273
MOULDING |  | Jan: 563461.38; Feb: 504487.28; Mar: 579283.13; Apr: 376638.64; May: 756495.02; Jun: 112325.09 | 2892690.54 | 723172.635 | 8678071.62 | 6675849.31 | 29.992
OTHER PRODUCTS |  | Jan: 2499888.25; Feb: 2510702.73; Mar: 3326473.85; Apr: 2773684.3; May: 2043239.95; Jun: 1984787.24 | 15138776.32 | 3784694.08 | 45416328.96 | 34061418.57 | 33.3366
FURNITURE /FURNITURE PARTS (UNT) |  | Jan: 6525963.7; Feb: 4146868.22; Mar: 5544565.16; Apr: 4798396.86; May: 6862929.99; Jun: 3423621.76 | 31302345.69 | 7825586.4225 | 93907037.07 | 53047079.74 | 77.0258
WOODEN PALLETS |  | Jan: 0; Feb: 0; Mar: 0; Apr: 0 | 0 | 0 | 0 | 11800 | -100
SCENTED WOOD |  | Jan: 14015.7; Feb: 0; Mar: 0; Apr: 0; May: 138319.9 | 152335.6 | 38083.9 | 457006.8 | 281097 | 100
CHARCOAL/BRIQUETTE |  | Jan: 651751.18; Feb: 892851.95; Mar: 675999.8; Apr: 652270.81; May: 992023.25; Jun: 562173.61 | 4427070.6 | 1106767.65 | 13281211.8 | 5450782.14 | 143.657
WOOD PELLETS |  | Jan: 7857849.72; Feb: 14034300; Mar: 0; Apr: 0; May: 20483496 | 42375645.72 | 10593911.43 | 127126937.16 | 44474036.16 | 185.8453
WOODCHIP |  | Jan: 17784168.67; Feb: 15858998.69; Mar: 20479005.19; Apr: 0; May: 18204994.92; Jun: 14066328.88 | 86393496.35 | 21598374.0875 | 259180489.05 | 179956709.76 | 44.0238
TOTAL (Jumlah) [RM'000] |  | 276004972.69 | 191530929.47 | 214907671.7 | 232014272.14 | 324627570.87 | 212303812.34 | 0 | 0 | 0 | 0 | 0 | 0 | 1451389229.21 | 362847307.3025 | 4354167687.63 | 3140839231.32 | 38.6307
% |  | 19.0166 | 13.1964 | 14.807 | 15.9857 | 22.3667 | 14.6276 | 0 | 0 | 0 | 0 | 0 | 0 | 100
OTHERS PRODUCTS: Blockboard,Dowels,Finger Jointed,Lamin Board, Laminated Beam/Post,
Laminated Veneer Lumber(LVL), Wooden Stakes.Wooden Handle
B. NUMBER OF EXPORT LICENSE OF LOG AND TIMBER PRODUCTS (JANUARY - DECEMBER 2024)
1. Number of license by products (Bilangan lesen mengikut produk)
Product (Produk) |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total (Jumlah) | Monthly Average (Purata bulanan) | Unjuran 2024 | Sebenar 2023 | Perubahan (%)
LOG (Natural Forest) |  | Jan: 219; Feb: 86; Mar: 124; Apr: 169 | 598 | 149.5 | 1794 | 1663 | 7.8773
LOG (Planted Forest) |  | Jan: 0; Feb: 0; Mar: 0 | 0 | 0 | 0 | 0 | 0
PLYWOOD |  | Jan: 261; Feb: 166; Mar: 210; Apr: 229 | 866 | 216.5 | 2598 | 2771 | -6.2432
SAWNTIMBER |  | Jan: 83; Feb: 36; Mar: 61; Apr: 82 | 262 | 65.5 | 786 | 848 | -7.3113
FIBREBOARD |  | Jan: 95; Feb: 77; Mar: 74; Apr: 98 | 344 | 86 | 1032 | 1034 | -0.19342
VENEER |  | Jan: 6; Feb: 7; Mar: 4; Apr: 8 | 25 | 6.25 | 75 | 103 | -27.1845
DOORSKIN |  | Jan: 36; Feb: 18; Mar: 25; Apr: 38 | 117 | 29.25 | 351 | 479 | -26.7223
LAMINATED BOARD/FLOORING |  | Jan: 16; Feb: 16; Mar: 13; Apr: 17 | 62 | 15.5 | 186 | 163 | 14.1104
PARTICLEBOARD |  | Jan: 7; Feb: 5; Mar: 3; Apr: 3 | 18 | 4.5 | 54 | 59 | -8.4746
DOOR PANELS & FRAMES |  | Jan: 40; Feb: 32; Mar: 33; Apr: 24 | 129 | 32.25 | 387 | 267 | 44.9438
MOULDING |  | Jan: 24; Feb: 27; Mar: 28; Apr: 16 | 95 | 23.75 | 285 | 214 | 33.1776
OTHER PRODUCTS |  | Jan: 27; Feb: 19; Mar: 27; Apr: 26 | 99 | 24.75 | 297 | 331 | -10.2719
FURNITURE /FURNITURE PARTS (UNT) |  | Jan: 26; Feb: 16; Mar: 18; Apr: 21 | 81 | 20.25 | 243 | 243 | 0
WOODEN PALLETS |  | Jan: 0; Feb: 0; Mar: 0; Apr: 0 | 0 | 0 | 0 | 1 | -100
SCENTED WOOD |  | Jan: 1; Feb: 0; Mar: 0; Apr: 0 | 1 | 0.25 | 3 | 2 | 100
CHARCOAL/BRIQUETTE |  | Jan: 9; Feb: 11; Mar: 10; Apr: 8 | 38 | 9.5 | 114 | 84 | 35.7143
WOOD PELLETS |  | Jan: 2; Feb: 3; Mar: 0; Apr: 0 | 5 | 1.25 | 15 | 24 | -37.5
WOODCHIP |  | Jan: 2; Feb: 1; Mar: 3; Apr: 0 | 6 | 1.5 | 18 | 19 | -5.2632
TOTAL (Jumlah) |  | 854 | 520 | 633 | 739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2746 | 686.5 | 8238 | 8305 | -0.80674
% |  | 31.0998 | 18.9366 | 23.0517 | 26.9119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
OTHERS PRODUCTS: Blockboard,Dowels,Finger Jointed,Lamin Board, Laminated Beam/Post,
Laminated Veneer Lumber(LVL), Wooden Stakes.Wooden Handle
2. Number of license per division approved by Royal Custom Department (Bilangan lesen setiap bahagian yang diluluskan oleh JKDM)
Division (Bahagian) |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total (Jumlah) | Monthly Average (Purata bulanan) | Unjuran 2024 | Sebenar 2023 | Perubahan (%)
Kuching |  | Jan: 10; Feb: 11; Mar: 7; Apr: 12 | 40 | 10 | 120 | 159 | -24.5283
Tg.Manis |  | Jan: 179; Feb: 62; Mar: 95; Apr: 136 | 472 | 118 | 1416 | 1197 | 18.2957
Sibu |  | Jan: 109; Feb: 80; Mar: 107; Apr: 107 | 403 | 100.75 | 1209 | 1342 | -9.9106
Bintulu |  | Jan: 291; Feb: 208; Mar: 229; Apr: 284 | 1012 | 253 | 3036 | 3272 | -7.2127
Miri |  | Jan: 265; Feb: 159; Mar: 195; Apr: 200 | 819 | 204.75 | 2457 | 2335 | 5.2248
Limbang |  | Jan: 0; Feb: 0; Mar: 0; Apr: 0 | 0 | 0 | 0 | 0 | 0
TOTAL (Jumlah) |  | 854 | 520 | 633 | 739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2746 | 686.5 | 8238 | 8305 | -0.80674
% |  | 31.0998 | 18.9366 | 23.0517 | 26.9119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100